TECHNICAL DESCRIPTION (PART B)

COVER PAGE

Part B of the Application Form must be downloaded from the Portal Submission System, completed and then assembled and re-uploaded as PDF in the system. Page 1 with the grey IMPORTANT NOTICE box should be deleted before uploading.

Note: Please read carefully the conditions set out in the Call document (for open calls: published on the Portal). Pay particular attention to the award criteria; they explain how the application will be evaluated.

PROJECT

Project name:

FAAM-ENI Circular Energy: Digital Twin-Driven LFP Active Material Manufacturing

Project acronym:

FACE

Coordinator contact:

[TO BE COMPLETED: Managing Director NAME], ESS (Eni Storage Systems) JV

TABLE OF CONTENTS

TECHNICAL DESCRIPTION (PART B)
        2

COVER PAGE
        2

PROJECT SUMMARY
        3

0. PROJECT AND APPLICANTS
        3

1. DEGREE OF INNOVATION
        4

1.1 Innovation in relation to the state of the art
        4

2. GHG EMISSION AVOIDANCE POTENTIAL
        4

2.1 Absolute GHG emission avoidance
        5

2.2 Relative GHG emission avoidance
        5

2.3 Minimum requirements
        5

3. PROJECT MATURITY
        6

3.1 Technical maturity
        6

3.2 Financial maturity
        7

3.3 Operational maturity
        8

3.4 Risk management
        10

4. REPLICABILITY
        10

4.1 Replicability
        10

4.2 Knowledge sharing — Communication, dissemination and visibility
        11

5. COST EFFICIENCY
        12

5.1 Relevant costs and cost efficiency ratio
        12

6. BONUS POINTS
        12

7. WORKPLAN, WORK PACKAGES, ACTIVITIES, MILESTONES, DELIVERABLES AND TIMING
        13

7.1 Work plan
        13

7.2 Work packages, activities, resources and timing
        13

Work Package 1
        15

Work Package 2
        17

Work Package 3
        20

Work Package 4
        22

Work Package N (last year of operation)
        24

Estimated budget — Resources
        26

Timetable
        26

8. OTHER
        27

8.1 Ethics
        27

8.2 Security
        27

9. DECLARATIONS
        27

ANNEXES
        29

#@APP-FORM-INNOVFUND@#

#@PRJ-SUM-PS@#  [This document is tagged. Do not delete the tags; they are needed for the processing.]

PROJECT SUMMARY

Project summary

See Abstract (Application Form Part A).

#§PRJ-SUM-PS§# #@REL-EVA-RE@# #@PRJ-OBJ-PO@#

0. PROJECT AND APPLICANTS

Background and objectives

Describe the background and rationale of the project as well as its specific objectives.

▶ §0.1 Background and objectives

0.1 Background and Objectives

The EU's Critical LFP Supply Chain Vulnerability

The European Union faces an acute and escalating dependency on China for lithium iron phosphate (LFP) cathode active material (CAM) — the fastest-growing battery chemistry for electric vehicles and grid-scale energy storage. China controls over 99% of global LFP CAM production capacity [CLM-001], with CATL, BYD, Gotion High-Tech, and Dynanonic dominating supply [SRC-022, SRC-023]. No EU-based company has brought LFP CAM production online as of late 2025 [CLM-003].

This dependency has moved from latent risk to active threat. In July 2025, China imposed export licensing requirements on 4th-generation LFP cathode technology. In October 2025, controls were broadened to battery cells, precursors, anode materials, and production equipment [CLM-002]. The German Council on Foreign Relations (DGAP) has urged the EU to urgently improve supply chain transparency and accelerate domestic LFP CAM manufacturing [SRC-024]. The European Parliament Research Service has framed the absence of EU-based LFP CAM production as a critical strategic gap requiring immediate industrial action [SRC-023].

The EU has responded with a comprehensive policy architecture — the Net-Zero Industry Act (NZIA), the Critical Raw Materials Act (CRMA), the EU Battery Regulation (including the Battery Passport by 2027), and the Innovation Fund — to develop domestic battery manufacturing capabilities [SRC-023, SRC-026]. The Innovation Fund had previously awarded EUR 122M to FREYR Battery (October 2024) for a planned 30,000 t/yr LFP CAM facility in Vaasa, Finland, confirming call eligibility and strategic priority for domestic LFP CAM manufacturing [CLM-004]. However, FREYR has since cancelled its Vaasa plans, citing a strategic pivot toward its US Giga America facility [CLM-029]. As a result, no LFP CAM production facility is currently active or under construction in the European Union, making the window for a first-mover European entrant both strategically urgent and commercially well-positioned.

Market Context and Policy Alignment

LFP has become the dominant battery chemistry for standard-range electric vehicles and grid-scale energy storage, driven by its superior safety (no thermal runaway), long cycle life (>6,000 cycles at cell level depending on architecture), and lower raw material cost compared to nickel-based alternatives [SRC-011, SRC-015]. The global LFP CAM market is growing at >25% CAGR through 2030, with demand driven by the EU's transport electrification targets and the rapid expansion of stationary energy storage for renewable grid integration. The target market for the Brindisi plant is primarily ESS cell manufacturers, where LFP's cycle life and safety advantages are decisive.

The EU's policy response to the battery supply chain vulnerability is comprehensive and urgent. The Net-Zero Industry Act (NZIA) mandates that at least 40% of the EU's annual deployment needs for key clean technologies — including batteries — should be manufactured domestically by 2030. The Critical Raw Materials Act (CRMA) targets diversification of supply chains for strategic materials including lithium and battery-grade processed materials. The EU Battery Regulation (2023/1542) introduces the Battery Passport by February 2027, requiring manufacturers to provide verified data on carbon footprint, recycled content, and material provenance — data that is inherently easier to provide for EU-manufactured products with full traceability [SRC-023, SRC-026]. The Innovation Fund, with EUR 1 billion allocated to the CLEAN-TECH-MANUFACTURING topic in the 2025 call, provides the direct co-financing mechanism for bridging the CAPEX gap in domestic battery material manufacturing [SRC-026].

Commission Communication C/2025/3236 of 18 June 2025 explicitly identifies battery cells, battery packs, and anode active materials as products with critical dependencies on third countries (primarily China), requiring mitigation actions under the NZIA framework [SRC-023]. While this communication focuses on cells and anode materials, the upstream dependency on Chinese LFP CAM is the root cause — without domestic cathode material supply, European cell manufacturers remain dependent on Chinese exports regardless of cell-level localisation.

The Brindisi Opportunity: A Vertically Integrated Clean Energy Hub

Eni's industrial site in Brindisi, Puglia, offers a brownfield conversion opportunity uniquely suited to LFP CAM manufacturing — and, critically, the Brindisi site is the location of a planned ESS (Eni Storage Systems) JV battery cell and BESS manufacturing facility that will be co-located with the LFP CAM plant. This creates a vertically integrated value chain from cathode material to grid-deployed energy storage within a single industrial site: LFP CAM produced by this project feeds directly into the co-located JV factory, which manufactures battery cells and assembles them into battery energy storage systems (BESS). Eni, as the direct internal customer, will deploy these BESS on the Italian electricity grid for grid stabilisation and decarbonisation. The full value chain is: LFP CAM (this project) to battery cells (JV factory) to BESS systems (JV factory) to Italian grid deployment (Eni).

The site provides existing industrial infrastructure — power supply connections, road and port access, and environmental permitting precedent — that substantially de-risks the construction timeline. Located in Southern Europe, the Brindisi plant would become the sole active LFP CAM production facility in the European Union following FREYR's cancellation of its Vaasa plans, serving Mediterranean and broader European battery cell manufacturers with full supply chain traceability.

Puglia's renewable energy trajectory — driven by one of Italy's highest solar irradiation levels and substantial onshore wind capacity — positions Brindisi as an increasingly decarbonized manufacturing location. Italy's NECP projects grid carbon intensity declining to approximately 146 gCO2/kWh by 2030 (65% renewable electricity), crossing the gas-breakeven threshold (~180 gCO2/kWh) by approximately 2027-2028 [CLM-025, CLM-026].

Project Objectives

The FAAM-ENI Circular Energy project will construct and operate the first LFP cathode active material production facility in Italy and Southern Europe [CLM-022], integrating electrified process heat with an ISO 23247-compliant digital twin for real-time process optimisation. The project pursues the following specific objectives:

1. Establish EU LFP CAM production capacity: Commission a production plant at Eni's Brindisi brownfield site capable of producing battery-grade LFP CAM (LiFePO4/C), directly reducing EU dependency on Chinese imports and addressing NZIA manufacturing benchmarks.

2. Progressively electrify process heat: Deploy electric roller hearth kiln calcination and heat pump-assisted spray drying, progressively replacing natural gas-fired thermal processes used by incumbent Asian producers. The initial plant design retains limited gas use (189 m3/t LFP CAM, primarily in spray drying and calcination auxiliary heating) while maximising electrification. The digital twin will optimise the energy mix and guide further gas-to-electric substitution as technology matures and the grid decarbonises. Target: 55-70% GHG reduction versus fully gas-fired benchmark by 2030, rising to 80-90% by 2035 as electrification deepens and grid intensity falls [CLM-026].

3. Implement the first digital twin for LFP CAM powder synthesis: Deploy an ISO 23247-compliant, multi-scale physics-based digital twin spanning the full production chain (spray drying, calcination, jet milling) with closed-loop model-predictive control (MPC). Target: scrap rate reduction 10-50%, energy consumption reduction 12-15%, batch-to-batch variability reduction >40% [CLM-007].

4. Achieve financial close within 2 years of grant agreement signature and entry into operation within 4 years, demonstrating the project maturity expected under the CLEAN-TECH-MANUFACTURING topic.

5. Generate primary LFP-specific lifecycle emission data: Through the plant's instrumented production line, produce the first published electrified LFP CAM lifecycle emission factors, addressing the documented research gap in LFP-specific GHG data [CLM-028].

Consortium: beneficiaries and other participants

Brief presentation of the applicant(s) (including any affiliated entities involved in the action) outlining areas of overall and project-specific expertise, number of employees, founding year, geographical locations. Explain why the applicant is the most suitable for implementing the project.

Describe the relationship between these participants in the project framework.

▶ §0.2 Consortium

0.2 Consortium

This proposal is submitted as a mono-beneficiary grant application with ESS (Eni Storage Systems) JV as the sole legal beneficiary and coordinator. ESS JV is a jointly owned entity of Eni S.p.A. and FIB S.p.A. (FAAM), both of which provide strategic direction, personnel, technical expertise, and infrastructure through shareholder and intercompany service arrangements. This mono-beneficiary structure reflects the integrated nature of the project: the applicant is the same legal entity that, under its broader industrial plan, will construct and operate the co-located battery cell and BESS manufacturing facility fed by this LFP CAM plant, ensuring full alignment between cathode material production, downstream battery manufacturing, and grid deployment.

ESS (Eni Storage Systems) JV — Sole Beneficiary and Coordinator

ESS JV is the joint venture company established by Eni S.p.A. and FIB S.p.A. (FAAM) to develop, construct, and operate Italy's first vertically integrated stationary lithium battery platform at the Brindisi site. ESS JV is registered as a legal entity in Italy, validated in the EU Funding & Tenders Portal Participant Register, and holds a Participant Identification Code (PIC) for Innovation Fund applications. The company operates under the combined governance of its parent shareholders and leverages personnel, technical know-how, and operational capabilities from both Eni and FIB.

ESS JV industrial scope: ESS JV owns and operates (a) this LFP cathode active material plant, (b) the co-located battery cell and BESS manufacturing facility (under parallel development at the same Brindisi site), and (c) the associated commercial and technology-licensing arrangements required for both facilities. The LFP CAM produced by this project is supplied directly and entirely to the ESS JV battery cell and BESS factory, which is the guaranteed internal customer for 100% of plant output.

Expertise and suitability as sole beneficiary:

• Direct legal ownership of the Brindisi brownfield site (contributed by Eni), removing site-acquisition risk

• Combined balance-sheet strength of Eni (one of Europe's largest energy companies, ~32,000 employees, EUR 90B+ revenue) and FIB (established battery manufacturer, ~354 employees), providing the financial capacity and operational track record required by the Innovation Fund financial capacity assessment

• Vertically integrated industrial plan: the same legal entity owning LFP CAM production, battery cell manufacturing, and BESS assembly — eliminating offtake risk and ensuring tight technical feedback between CAM quality and downstream cell performance

• Personnel drawn from both shareholders' existing operations: battery manufacturing expertise from FIB's Teverola site, process engineering and energy management from Eni's petrochemical and power operations at Brindisi

• Responsible for: plant design, construction management, LFP CAM process operation, digital twin development and integration, product qualification, downstream integration with cell and BESS manufacturing, and ongoing operations

Shareholder 1: Eni S.p.A. — Industrial Partner and Site Provider

Eni is one of Europe's largest integrated energy companies, with approximately 32,000 employees globally and revenues exceeding EUR 90 billion. Founded in 1953 and headquartered in Rome, Italy, Eni operates across the energy value chain with increasing investment in decarbonisation and clean technology.

Contribution to ESS JV:

• Owner and operator of the Brindisi industrial site, providing brownfield infrastructure for accelerated construction (site contributed to ESS JV under the joint venture agreement)

• Extensive process engineering capabilities in large-scale thermal, chemical, and petrochemical operations — available to ESS JV through intercompany secondment and technical services agreements

• Expertise in energy supply, grid integration, and renewable energy procurement — critical for the progressively electrified manufacturing model

• Established environmental management, permitting, and community engagement track record at the Brindisi site

• Downstream BESS grid deployment: Eni acts as the commercial offtaker for BESS systems manufactured by the ESS JV battery factory, deploying them on the Italian electricity grid for grid stabilisation and decarbonisation services. This ensures guaranteed end-use demand for ESS JV's combined cathode material and battery manufacturing output.

• Seconded personnel: process engineers, environmental and permitting specialists, energy supply architects, project development managers

Shareholder 2: FIB S.p.A. (FAAM) — Industrial Partner and Battery Manufacturing Expertise

FIB S.p.A., operating under the FAAM brand, is an Italian battery manufacturer founded in 1974, with over 50 years of experience in lead-acid and lithium-ion battery production. A subsidiary of Seri Industrial S.p.A., FIB is headquartered in Monterubbiano (FM), Marche, Italy, where its first factories were established in 1976. FIB employs approximately 354 staff across its manufacturing and R&D operations. FIB's Li-ion cell manufacturing activities are based at the Teverola site in the Province of Caserta, Campania (near Naples), where it operates two facilities: Teverola 1, a 300 MWh/year Li-ion soft pouch cell production plant currently in operation, and Teverola 2, an 8 GWh/year cell manufacturing plant under development. The company produces lithium-ion batteries for traction, industrial, storage, and military applications, as well as lead-acid batteries and fuel cells, with a strategic focus on green batteries with low environmental impact. FIB has a strong track record of supporting research through university partnerships, including PhD studentships and MSc degree collaborations.

Contribution to ESS JV:

• Established battery manufacturing operations with ISO 9001, ISO 14001, and ISO 45001 management systems — directly transferable to ESS JV

• Direct experience in scaling battery cell production from pilot to commercial volumes (Teverola 1 to Teverola 2)

• Track record in EU-funded collaborative projects in the battery value chain

• Existing relationships with European battery ecosystem actors (cell manufacturers, materials suppliers, research institutions)

• Seconded personnel: battery materials engineers, cell manufacturing specialists, quality control experts, product qualification managers, and research collaboration coordinators

Technology Licensor: Zhejiang Youshan New Material Technology Co., LTD.

ESS JV has secured a technology licensor for the LFP CAM solid-state synthesis process — Zhejiang Youshan New Material Technology Co., LTD. (hereafter "Youshan") — providing process know-how, recipe optimisation, and equipment specification support. Youshan brings proven industrial experience in LFP CAM production, de-risking the scale-up from established process parameters to the Brindisi plant's specific configuration and throughput requirements. The licensor relationship covers process recipe definition, calcination profile optimisation, and spray drying parameter specification, while ESS JV retains ownership of the digital twin integration and progressive electrification innovations developed during the project.

Co-Located Battery Cell and BESS Manufacturing Facility

Under ESS JV's broader industrial plan, a battery cell and BESS manufacturing facility is being developed in parallel on the same Brindisi industrial site. This co-located facility will convert the LFP CAM produced by this project into battery cells and assemble them into grid-scale battery energy storage systems (BESS). The cells and BESS will be supplied to Eni for deployment on the Italian electricity grid as part of Eni's strategy to stabilise and decarbonise the Italian power system. Because ESS JV owns both the CAM plant and the cell/BESS facility, this creates a mine-to-grid vertically integrated value chain within a single legal entity and site, eliminating offtake risk and ensuring seamless technical integration. The parallel development of the cell and BESS facility is coordinated with the LFP CAM plant timeline to ensure simultaneous ramp-up upon entry into operation.

Governance and Personnel Model

ESS JV operates under the governance of its shareholders (Eni and FIB), with a joint board of directors and operational management appointed from both parent companies. Day-to-day operations are delivered by a mix of directly employed ESS JV staff and personnel seconded from Eni and FIB under intercompany service agreements. This hybrid model allows ESS JV to leverage the deep operational experience of both shareholders — Eni's process engineering and energy expertise, FIB's battery manufacturing and materials expertise — while maintaining a single legal and contractual interface with the Innovation Fund, technology suppliers, and commercial counterparties. Decision-making is governed by a joint steering committee with defined escalation protocols to the shareholder boards for strategic matters.

Technical characteristics and scope

Outline the technical characteristics and scope of the project.

Include information on:

project location and site

technology (and why this has been chosen over alternatives)

expected source of key inputs and feedstock

expected output in terms of volume of main product(s)

▶ §0.3 Technical characteristics and scope

0.3 Technical Characteristics and Scope

Project Location and Site

The plant will be located at Eni's existing industrial site in Brindisi, Puglia, Italy (40.615°N, 17.980°E), located just south of the city near the industrial port area and Punta della Contessa, within the broader multi-company petrochemical hub (Versalis, Enipower, Basell) managed by Eni Rewind for soil and groundwater remediation. The site includes an Enipower combined-cycle power plant facing the Adriatic Sea). The Brindisi site offers:

• Existing industrial zoning and environmental permitting precedent

• Grid-connected power supply infrastructure with capacity for electrified manufacturing loads

• Road access (SS 613, E55 corridor) and port access (Port of Brindisi) for raw material import and product distribution

• Proximity to Southern European battery cell manufacturing operations

LFP CAM Technology: Solid-State Synthesis Route

The plant employs the solid-state synthesis route — the dominant industrial process for LFP CAM production globally [SRC-011]. This route is selected for its excellent scalability, established process knowledge, and compatibility with electrified heating systems. The process involves stoichiometric mixing of precursors, wet milling, spray drying for particle engineering, and calcination under inert atmosphere to form phase-pure olivine LiFePO4 with in-situ carbon coating.

The manufacturing process comprises a 7-step production chain:

Step  |  Operation  |  Key Parameters

1  |  Raw materials dosing  |  Iron phosphate (0.98 t/t), lithium carbonate (0.25 t/t), glucose (0.010 t/t), TiO2 (0.008 t/t), H3PO4 (0.006 t/t) into dispersion tank

2  |  Bead milling + magnetic separation  |  Particle size reduction, demagnetisation

3  |  Spray drying  |  Aqueous slurry to solid unreacted mixture; controls morphology

4  |  Crucible loading + calcination  |  Electric roller hearth kiln, 700-800 C under N2 (pO2 <10 ppm)

5  |  Jet milling  |  Air-flow grinding to target D50 0.7-2.5 um

6  |  Ultrasonic sieving + demagnetisation  |  Classification and magnetic particle removal

7  |  Automated packaging  |  Final product: battery-grade LiFePO4/C

Key Inputs and Feedstock

• Iron phosphate (FePO4): Primary iron and phosphorus source. Consumption: 0.98 t per tonne LFP CAM (49,000 t/yr at full capacity). Sourced from diversified suppliers including European and non-Chinese sources, subject to off-take negotiations

• Lithium carbonate (Li2CO3): Primary lithium source. Consumption: 0.25 t per tonne LFP CAM (12,500 t/yr at full capacity). Sourced from multiple qualified suppliers including Australian, Chilean, and European refiners to ensure supply chain diversification

• Glucose (C6H12O6): Carbon source for in-situ carbon coating during calcination. Consumption: 0.010 t per tonne LFP CAM (500 t/yr at full capacity). Commodity chemical available from European suppliers

• TiO2: Doping/coating additive. Consumption: 0.008 t per tonne LFP CAM (400 t/yr at full capacity)

• H3PO4: Supplementary phosphorus source. Consumption: 0.006 t per tonne LFP CAM (300 t/yr at full capacity)

Expected Output

The plant is designed for an annual production capacity of 50,000 tonnes (50 kton/yr) of battery-grade LFP CAM, organised across 4 modular production lines of 12,500 t/yr each. The plant produces two product grades: nanosized LFP (75% of output) and spherical LFP (25% of output), the latter achieved through a configurable spray-drying and optional jet-milling bypass. The workshop footprint is approximately 161.1 m x 106 m (~17,100 m2). The production process employs flexible solid-state synthesis with configurable spray-drying, calcination in saggars under N2 atmosphere, and optional jet-milling bypass for the spherical grade. The product meets the following specifications:

Quality Attribute  |  Target Specification

D10 particle size  |  0.3-1.0 um

D50 particle size  |  0.7-2.5 um

D90 particle size  |  2.5-12.0 um

Specific surface area (SSA)  |  10-14 m2/g

Tap density  |  1.0-1.4 g/cm3

Pellet density  |  >=2.40 g/cm3

Electrode press density  |  >=2.30 g/cm3

Carbon content  |  1.0-1.8 wt%

Moisture  |  <750 ppm

Magnetic impurities  |  <=1000 ppb

Discharge capacity (0.1C)  |  >=155 mAh/g

Discharge capacity (1C)  |  >=140 mAh/g

Initial Coulombic Efficiency (ICE)  |  ~98%

Phase purity (olivine)  |  >98% by XRD Rietveld

Technology scope and the chosen technological solution

Describe in detail the technology/solution applied, and expected impacts of the technology and processes associated with the plant, with reference to the category, sector and product proposed.

Describe the technology construction, operation and maintenance plan, including operation assumptions and sensitivities. The description should also cover safety, reliability, technical performance and relevant standards.

Describe the critical interfaces between the different technical components and how interface issues are handled.

▶ §0.4 Technology scope

0.4 Technology Scope

Electrified Manufacturing

The central technology choice is a progressive electrification strategy for process heat in spray drying and calcination — the two most energy-intensive steps in LFP CAM production. The plant is designed to maximise electricity use from day one while retaining limited natural gas capacity (189 m3/t LFP CAM in the initial configuration) for process steps where full electrification is not yet technically or economically feasible at production scale. This represents a fundamental departure from the gas-fired rotary kilns and gas-heated spray dryers used by all incumbent Chinese LFP CAM producers [CLM-001, SRC-022], achieving a significantly higher degree of electrification than the Asian gas-fired benchmark.

Spray drying electrification: Heat pump-assisted pre-heating (high-temperature heat pump at COP 3.04-3.6 [SRC-ED-004, SRC-ED-005]) combined with electric resistance or NIR final drying [SRC-ED-019], replacing natural gas burners.

Calcination electrification: Electric roller hearth kiln operating at 700-800 C under N2 atmosphere, achieving 95% thermal efficiency versus 25-60% for gas-fired kilns [CLM-023]. Electric roller hearth kilns are the established industrial standard for NMC CAM calcination (Jo et al., 2025; NGK vendor data [SRC-ED-010, SRC-ED-023]) and are directly applicable to LFP calcination temperatures and atmosphere requirements.

Future-proof design rationale: Italy's current grid carbon intensity (~310 gCO2/kWh) is marginal for GHG benefits versus gas combustion. However, the plant is designed for a 20+ year operational life. Italy's NECP trajectory projects grid intensity declining to ~146 gCO2/kWh by 2030 and ~30-60 gCO2/kWh by 2035 (G7 commitment). Electrification now locks in infrastructure compatible with the decarbonised grid of the 2030s, before fossil-fuel-based process heating becomes stranded [CLM-030].

ISO 23247 Digital Twin Integration

The production plant integrates an ISO 23247-compliant digital twin — the first for LFP CAM powder synthesis [CLM-005]. The digital twin architecture follows the ISO 23247 four-layer model [SRC-007, SRC-008]:

1. Observable Manufacturing Element (OME): The 7-step physical production line instrumented with PAT sensors

2. Data Collection and Device Control (DCDC): Edge gateways, OPC-UA/MQTT protocols, PLC interfaces for real-time bidirectional data exchange

3. Digital Twin Core Entity: Multi-scale physics-based models (CALPHAD thermodynamics, CFD for calcination, population balance models, DEM for milling, reaction kinetics) integrated with machine learning surrogates for real-time prediction [CLM-018]

4. User Entity: Model-predictive control (MPC) interfaces, quality prediction dashboards, predictive maintenance modules

The DT core entity implements a QbD/PAT framework adapted from pharmaceutical manufacturing (ICH Q8), systematically mapping Critical Quality Attributes (D50, BET, phase purity, carbon content, capacity) to Critical Process Parameters across all 7 process steps [CLM-009]. In-line sensors (Raman spectroscopy, FBRM, pyrometry, O2 monitoring) feed real-time data to the DT for closed-loop process adjustment [CLM-019].

Why Electrified Manufacturing Over Gas-Fired Alternatives

The choice of electrified process heat over the incumbent gas-fired approach is driven by three converging factors:

1. Climate alignment: Per Section 1.3.4 of the Innovation Fund GHG methodology, the GHG avoidance is calculated on the use phase of the manufactured battery components (ESS systems containing LFP CAM), not on the manufacturing plant itself. The plant's progressive electrification (66.6% at entry into operation) nonetheless delivers a substantially lower product carbon footprint than gas-fired competitors, strengthening the innovation case and long-term competitiveness. As Italy's grid decarbonises (~146 gCO2/kWh by 2030), the electrified plant's embedded carbon advantage compounds [CLM-026].

2. Process quality advantage: Electric heating provides superior temperature uniformity compared to gas flame heating. In LFP calcination, temperature variations of as little as 50 C can shift the product from phase-pure olivine to impurity-contaminated material (Li3PO4, Fe2P above 800 C) [SRC-011, CLM-020]. Electric roller hearth kilns enable zone-by-zone temperature control with precision compatible with DT-driven MPC, a capability that gas-fired rotary kilns cannot match.

3. Stranded asset avoidance: A gas-fired plant built today would face escalating carbon costs under the EU ETS, potential regulatory restrictions on new fossil fuel infrastructure, and eventual conversion costs. Electrifying from the outset eliminates these risks and positions the plant as a first mover in clean LFP CAM manufacturing.

Critical Interfaces Between Technical Components

The technical architecture involves three critical interfaces that determine system performance:

Interface 1: PAT sensors to DT (DCDC layer): The sensor network generates approximately 50-100 data streams at frequencies ranging from 0.1 Hz (at-line XRD) to 10 Hz (IR camera). The OPC-UA/MQTT data pipeline must aggregate, timestamp, and deliver this data to the DT core within 100 ms for real-time applications. Edge computing nodes at each major process step (spray dryer, kiln, mill) perform initial signal processing and anomaly detection before cloud transmission.

Interface 2: DT core to MPC (User Entity layer): The physics-based surrogate models in the DT core compute quality predictions and optimal setpoints. These must be translated to PLC-compatible control signals via the MPC interface. The MPC operates on a receding-horizon basis: 5-15 minute horizons for calcination (thermal inertia), 1-3 minute horizons for spray drying (faster dynamics), and millisecond-level for milling classifier speed. Process constraints (temperature limits, atmosphere limits, equipment rated capacities) are encoded as hard constraints in the MPC optimisation.

Interface 3: Electric RHK to atmosphere control: The kiln atmosphere (N2 with pO2 <10 ppm) must be maintained while allowing product entry and exit via the roller conveyor. Gas-tight sealing at kiln entry/exit zones, N2 curtain flow, and continuous pO2 monitoring with automatic N2 purge response form the critical path. The DT models kiln atmosphere dynamics to predict and pre-empt O2 ingress events.

Construction, Operation, and Maintenance

Construction phase (target: 24 months from FID): Brownfield site preparation, equipment procurement and installation (spray dryer, electric roller hearth kiln, jet mill, PAT sensor network, DT computing infrastructure), commissioning and process qualification.

Operation: Continuous production with batch calcination cycles. The DT enables condition-based monitoring of all critical equipment, reducing unplanned downtime through predictive maintenance — a benefit demonstrated at 20-50% downtime reduction in comparable process industry DT deployments [CLM-007].

Maintenance: Condition-based maintenance driven by DT-derived equipment health indicators, replacing calendar-based maintenance schedules. Virtual sensing capabilities allow monitoring of parameters that cannot be directly measured in real-time (e.g., internal kiln atmosphere composition gradients), extending sensor coverage without additional hardware.

Safety, Reliability, and Technical Performance

Safety: LFP CAM production operates below 700 C under inert atmosphere — significantly lower risk than NMC synthesis (which requires reactive lithium hydroxide and temperatures to 950 C). The inert atmosphere (N2) and the progressive electrification design (minimising on-site gas combustion) reduce fire and explosion risk compared to fully gas-fired equivalents. A comprehensive safety programme including HAZID/HAZOP studies and ATEX (explosive atmosphere) assessment is mandated for the detailed engineering phase, addressing powder handling safety, dust control, and residual gas infrastructure. Standard industrial safety protocols for powder handling (dust explosion prevention), chemical handling (lithium carbonate, iron phosphate), and high-temperature equipment apply. The facility will be managed under ISO 45001 occupational health and safety standards.

Reliability: The DT-driven predictive maintenance approach targets >92% overall equipment effectiveness (OEE), compared to industry averages of 75-85% for batch chemical manufacturing. Electric heating elements (SiC, Kanthal Tubothal/Fibrothal) have demonstrated lifetimes exceeding 10,000 operating hours at temperatures up to 1100 C [SRC-ED-009].

Technical performance: The product quality specifications (Section 0.3) define the design space within which the DT's MPC system operates. The closed-loop control architecture ensures that process excursions are detected and corrected within a single control cycle (target: <60 seconds for calcination temperature, <5 minutes for spray drying outlet conditions), maintaining product quality within specification without operator intervention.

#§PRJ-OBJ-PO§# #§REL-EVA-RE§# #@IMP-ACT-IA@#

1. DEGREE OF INNOVATION

1.1 Innovation in relation to the state of the art

State-of-the-art

Describe the state-of-the-art of the solution(s) the project aims to demonstrate.

Cover the characteristics of the commercially available process or service that is most similar to the proposed one (commercial state-of-the-art), the already demonstrated characteristics of the proposed technological solution at the highest technological readiness level (technological state-of-the-art) and, where relevant, the innovative elements already demonstrated/used in other Innovation Fund projects (Innovation Fund Project Portfolio Dashboard).

This should focus on the European, rather than national level (or, for NZT GENERAL-SSP topic, on the European or national level).

▶ §1.1 State of the art

Commercial State-of-the-Art

Global LFP cathode active material production is dominated by Chinese manufacturers. CATL, BYD, Gotion High-Tech, and Dynanonic collectively control over 99% of global capacity [CLM-001], with all commercial-scale plants located in China [SRC-022, SRC-023]. No European manufacturer operates a commercial LFP CAM production line [CLM-003].

The commercial production process at incumbent Chinese facilities follows a well-established pattern:

• Thermal processing: Natural gas-fired rotary kilns for calcination at 700-800 C and gas-heated spray dryers for precursor drying. Gas-fired kilns achieve 25-60% thermal efficiency depending on heat recovery configuration [CLM-023, SRC-ED-009]. Gas combustion introduces combustion products into the kiln atmosphere, complicating the strict pO2 control (<10 ppm under N2) required for phase-pure olivine formation.

• Process control: Recipe-based, empirical approaches. Calcination temperature profiles, dwell times, and atmosphere conditions are fixed based on historical production experience. Process adjustment occurs between batches based on offline quality testing of finished product, not during production. Wang et al. (2023, 50 citations) explicitly identified the gap in theoretical models and in-line monitoring for industrial cathode precursor synthesis [SRC-028, CLM-013].

• Quality assurance: Offline batch testing after production completion. Critical quality attributes (D50, BET, phase purity, carbon content, discharge capacity) are measured at-line or off-line using XRD, BET analysis, particle size analysis, and electrochemical testing. There is no real-time, in-process quality prediction capability in current commercial LFP CAM production.

• Digital integration: No published evidence of integrated digital twin technology deployed in any commercial LFP CAM production facility. Chinese producers may have unpublished proprietary systems, but systematic searches across two independent review papers (Ayerbe et al., 2021 [SRC-001]; Dubarry et al., 2023 [SRC-002]), the patent landscape (12 patents analysed including CNIPA), and a 35-page deep-dive technical report [SRC-DT-REPORT] confirm this gap. The ARTISTIC group (U. Picardie Jules Verne) explicitly scoped their work to electrode manufacturing, not CAM synthesis [SRC-004, CLM-006].

Innovation Fund portfolio context: FREYR Battery received EUR 122M (October 2024) for a 30,000 t/yr LFP CAM facility in Vaasa, Finland [SRC-025]. However, FREYR has not specified progressive electrification of process heat, has not reached FID for Vaasa, and is currently prioritising its US Giga America facility [CLM-029]. The FAAM-ENI project differentiates on three axes: (i) progressively electrified process heat (66.6% electrification at entry into operation, with a roadmap to >95%); (ii) integrated ISO 23247 digital twin; and (iii) a more advanced project maturity trajectory with a committed brownfield site and co-investor (Eni).

Technological State-of-the-Art

The technological frontier relevant to this project spans three domains: digital twins for battery manufacturing, electrification of industrial process heat, and process analytical technology for powder manufacturing.

Digital Twins in Battery Manufacturing

Three principal DT implementations define the technological state-of-the-art:

ARTISTIC Platform (Franco group, Universite de Picardie Jules Verne; ERC-funded) [SRC-003, SRC-004]: The most comprehensive DT for battery electrode manufacturing. Employs a multi-scale simulation chain: coarse-grained molecular dynamics for slurry preparation, lattice models for coating/drying, discrete element method (DEM) for calendering, lattice Boltzmann method (LBM) for electrolyte filling, and finite element method (FEM, Newman P2D) for electrochemical performance. Validated for NMC111, NMC622, LFP, graphite, and silicon-graphite electrodes. Key achievement: Bayesian optimisation-driven inverse design finds optimal manufacturing parameters in fewer than 50 iterations (Duquesnoy et al., 2022, 81 citations in Energy Storage Materials [SRC-004]). Critical limitation: ARTISTIC addresses electrode-level manufacturing (slurry to cell), not upstream CAM powder synthesis from precursors [CLM-006].

TwinHeat (MINES Paris industrial chair) [SRC-DT-REPORT]: Industrial DTs for heat treatment optimisation of furnaces. Uses a dual AI loop: (1) CFD-generated training data combined with neural network surrogates for real-time temperature prediction, and (2) deep reinforcement learning for energy-optimal furnace control. Has demonstrated 10-15% energy reduction and <1 C prediction accuracy on carburising, nitriding, and quenching furnaces [CLM-016]. The approach is directly transferable to calcination furnace DT, substituting carburising chemistry with LFP reaction kinetics. Critical limitation: Applied to metallurgical heat treatment, not battery CAM synthesis.

Fraunhofer ITWM DiBaZ [SRC-DT-REPORT]: DT covering all process steps in battery cell production, from electrode coating through formation. Includes inline CT quality control, physics-based drying/calendering/filling models, and autoencoder-based anomaly detection. Fraunhofer FFB has reported a 10.3% scrap rate reduction using DT-guided process optimisation [CLM-017]. Critical limitation: Covers cell-level production, not CAM powder synthesis.

Li et al. (2024) [SRC-006]: DT for LFP battery pack assembly line optimisation — 3D digital representation enabling production flow simulation. Addresses pack assembly only.

Ma et al. (2023) [SRC-014]: Predictive model for NMC811 sintering furnace integrating chemical reactions, thermal conduction, and CFD. Validated with <10% error. Represents a physics-based process model applicable to calcination but was not implemented as an integrated DT.

The gap: No published or patented digital twin exists for upstream CAM powder production from precursors [CLM-005]. The spray drying to calcination to milling chain — where final CAM quality is determined — has no DT coverage in the literature. This gap is confirmed by two independent review papers (Ayerbe et al., 2021, 124 citations [SRC-001]; Dubarry et al., 2023, 38 citations in Joule [SRC-002]) and the comprehensive deep-dive report [SRC-DT-REPORT].

ISO 23247 Digital Manufacturing Framework

ISO 23247 (2021) defines the reference architecture for manufacturing DTs through a four-layer functional model [SRC-007, SRC-008]. Published implementations include:

• Shao (2021, NIST): Three use cases on the NIST Smart Manufacturing Systems Test Bed for CNC machining — the definitive ISO 23247 reference (43 citations) [SRC-007]

• Cabral et al. (2023): ISO 23247-compliant DT for CNC milling centre using MQTT and MTConnect [SRC-009]

• Melo et al. (2024): ISO 23247-compliant DT for automotive body shop inspection enabling zero defect manufacturing [SRC-010]

All published ISO 23247 implementations are in discrete manufacturing (machining, assembly) or additive manufacturing. No peer-reviewed implementation exists for thermal/chemical powder synthesis processes [CLM-008]. Applying ISO 23247 to continuous/batch chemical manufacturing where the standard must accommodate reaction kinetics feedback, atmosphere control, and multi-phase transformations is an undemonstrated extension.

Electrification of Industrial Process Heat

Industrial process heating accounts for approximately 20% of global CO2 emissions [CLM-010, SRC-018]. Electrification technologies for high-temperature heat (>400 C) are technically proven [SRC-016, SRC-017]:

• Electric resistance heating: mature at TRL 7-9 for kilns, achieving 95% thermal efficiency versus 25-60% for gas [CLM-023, SRC-ED-009]

• Electric roller hearth kilns: the established industrial standard for NMC CAM calcination, with validated CFD models (Jo et al., 2025 [SRC-ED-010]) and commercial equipment (NGK [SRC-ED-023])

• High-temperature heat pumps (HTHP): demonstrated at COP 3.04-3.6 for spray dryer pre-heating [SRC-ED-004, SRC-ED-005]

Electrified calcination has been demonstrated in cement (Liu et al., 2023 [SRC-019]) and lime (Dylong et al., 2025 [SRC-020]). Kanthal (Sandvik Group) documents 95% thermal efficiency for electric kilns versus 25-60% for gas kilns in battery material applications [SRC-ED-009].

The gap: No published work validates progressively electrified process heat (spray drying + calcination) specifically for LFP CAM synthesis at production scale [GAP-003]. Electric roller hearth kilns exist; HTHP-assisted spray drying exists; the specific combination applied to LFP CAM with its strict atmosphere (pO2 <10 ppm), temperature profile (700-800 C), and product quality requirements (phase-pure olivine) has not been demonstrated.

Technological State-of-the-Art

The technological frontier relevant to this project spans three domains: digital twins for battery manufacturing, electrification of industrial process heat, and process analytical technology for powder manufacturing.

Digital Twins in Battery Manufacturing

Three principal DT implementations define the technological state-of-the-art:

ARTISTIC Platform (Franco group, Universite de Picardie Jules Verne; ERC-funded) [SRC-003, SRC-004]: The most comprehensive DT for battery electrode manufacturing. Employs a multi-scale simulation chain: coarse-grained molecular dynamics for slurry preparation, lattice models for coating/drying, discrete element method (DEM) for calendering, lattice Boltzmann method (LBM) for electrolyte filling, and finite element method (FEM, Newman P2D) for electrochemical performance. Validated for NMC111, NMC622, LFP, graphite, and silicon-graphite electrodes. Key achievement: Bayesian optimisation-driven inverse design finds optimal manufacturing parameters in fewer than 50 iterations (Duquesnoy et al., 2022, 81 citations in Energy Storage Materials [SRC-004]). Critical limitation: ARTISTIC addresses electrode-level manufacturing (slurry to cell), not upstream CAM powder synthesis from precursors [CLM-006].

TwinHeat (MINES Paris industrial chair) [SRC-DT-REPORT]: Industrial DTs for heat treatment optimisation of furnaces. Uses a dual AI loop: (1) CFD-generated training data combined with neural network surrogates for real-time temperature prediction, and (2) deep reinforcement learning for energy-optimal furnace control. Has demonstrated 10-15% energy reduction and <1 C prediction accuracy on carburising, nitriding, and quenching furnaces [CLM-016]. The approach is directly transferable to calcination furnace DT, substituting carburising chemistry with LFP reaction kinetics. Critical limitation: Applied to metallurgical heat treatment, not battery CAM synthesis.

Fraunhofer ITWM DiBaZ [SRC-DT-REPORT]: DT covering all process steps in battery cell production, from electrode coating through formation. Includes inline CT quality control, physics-based drying/calendering/filling models, and autoencoder-based anomaly detection. Fraunhofer FFB has reported a 10.3% scrap rate reduction using DT-guided process optimisation [CLM-017]. Critical limitation: Covers cell-level production, not CAM powder synthesis.

Li et al. (2024) [SRC-006]: DT for LFP battery pack assembly line optimisation — 3D digital representation enabling production flow simulation. Addresses pack assembly only.

Ma et al. (2023) [SRC-014]: Predictive model for NMC811 sintering furnace integrating chemical reactions, thermal conduction, and CFD. Validated with <10% error. Represents a physics-based process model applicable to calcination but was not implemented as an integrated DT.

The gap: No published or patented digital twin exists for upstream CAM powder production from precursors [CLM-005]. The spray drying to calcination to milling chain — where final CAM quality is determined — has no DT coverage in the literature. This gap is confirmed by two independent review papers (Ayerbe et al., 2021, 124 citations [SRC-001]; Dubarry et al., 2023, 38 citations in Joule [SRC-002]) and the comprehensive deep-dive report [SRC-DT-REPORT].

ISO 23247 Digital Manufacturing Framework

ISO 23247 (2021) defines the reference architecture for manufacturing DTs through a four-layer functional model [SRC-007, SRC-008]. Published implementations include:

• Shao (2021, NIST): Three use cases on the NIST Smart Manufacturing Systems Test Bed for CNC machining — the definitive ISO 23247 reference (43 citations) [SRC-007]

• Cabral et al. (2023): ISO 23247-compliant DT for CNC milling centre using MQTT and MTConnect [SRC-009]

• Melo et al. (2024): ISO 23247-compliant DT for automotive body shop inspection enabling zero defect manufacturing [SRC-010]

All published ISO 23247 implementations are in discrete manufacturing (machining, assembly) or additive manufacturing. No peer-reviewed implementation exists for thermal/chemical powder synthesis processes [CLM-008]. Applying ISO 23247 to continuous/batch chemical manufacturing where the standard must accommodate reaction kinetics feedback, atmosphere control, and multi-phase transformations is an undemonstrated extension.

Electrification of Industrial Process Heat

Industrial process heating accounts for approximately 20% of global CO2 emissions [CLM-010, SRC-018]. Electrification technologies for high-temperature heat (>400 C) are technically proven [SRC-016, SRC-017]:

• Electric resistance heating: mature at TRL 7-9 for kilns, achieving 95% thermal efficiency versus 25-60% for gas [CLM-023, SRC-ED-009]

• Electric roller hearth kilns: the established industrial standard for NMC CAM calcination, with validated CFD models (Jo et al., 2025 [SRC-ED-010]) and commercial equipment (NGK [SRC-ED-023])

• High-temperature heat pumps (HTHP): demonstrated at COP 3.04-3.6 for spray dryer pre-heating [SRC-ED-004, SRC-ED-005]

Electrified calcination has been demonstrated in cement (Liu et al., 2023 [SRC-019]) and lime (Dylong et al., 2025 [SRC-020]). Kanthal (Sandvik Group) documents 95% thermal efficiency for electric kilns versus 25-60% for gas kilns in battery material applications [SRC-ED-009].

The gap: No published work validates progressively electrified process heat (spray drying + calcination) specifically for LFP CAM synthesis at production scale [GAP-003]. Electric roller hearth kilns exist; HTHP-assisted spray drying exists; the specific combination applied to LFP CAM with its strict atmosphere (pO2 <10 ppm), temperature profile (700-800 C), and product quality requirements (phase-pure olivine) has not been demonstrated.

Innovation beyond state-of-the-art

Describe how the project (technologies/products/services/processes/business models) goes beyond both the commercial and technological state-of-the-art, referring to key performance data evidenced in the feasibility study annex, covering at least:

plant design

operating approach

construction

performance/quality

reliability and availability

maintenance

economics.

Describe how the project (technologies/products/services/processes/business models) goes beyond incremental innovation, referring to key performance data evidenced in the feasibility study annex and covering at least:

expected increases in technology readiness level, system readiness level and/or commercial readiness level

the technological and economical barriers to be overcome in the realisation of the project.

See examples in Annex 1 of the Call document.

Explain why the proposed scale is the most appropriate to reach the objectives of the action.

▶ §1.1 Innovation beyond SOTA

Innovation Beyond the State-of-the-Art

The FAAM-ENI project delivers innovation across four pillars — plus a transformative structural innovation — each addressing a documented gap in the current state-of-the-art. The innovation is not incremental: it creates capabilities that do not currently exist at any scale, combining technologies that have been proven independently but never integrated for LFP CAM manufacturing.

Structural Innovation: Vertically Integrated Mine-to-Grid Value Chain

Beyond the four technology pillars, the project embodies a structural innovation of strategic significance: the LFP CAM plant is co-located with a planned ESS (Eni Storage Systems) JV battery cell and BESS manufacturing facility at the same Brindisi site. The full value chain — LFP CAM production (this project), battery cell manufacturing (JV factory), BESS system assembly (JV factory), and Italian grid deployment (Eni) — operates within a single consortium and industrial site. This vertically integrated architecture is unprecedented in the European battery sector and delivers compounding innovation benefits: (i) immediate quality feedback from cell manufacturing to CAM process optimisation via the DT, enabling a closed-loop quality improvement cycle that no standalone CAM producer can replicate; (ii) secured internal offtake eliminating market risk; and (iii) an end-to-end European battery value chain from raw materials to grid-deployed energy storage, directly serving EU strategic autonomy objectives. This is not merely a CAM factory — it is an integrated clean energy manufacturing hub.

Innovation Pillar 1: First Digital Twin for LFP CAM Powder Synthesis [NOV-001]

Defensibility score: 8/10 — highest novelty anchor

What is new: An integrated digital twin spanning the full LFP CAM production chain — from spray drying through calcination to jet milling — providing real-time quality prediction and closed-loop process control. This fills the documented gap between electrode-level DTs (ARTISTIC [SRC-004]) and cell-level DTs (DiBaZ [SRC-DT-REPORT]).

Multi-scale modelling framework: The DT core entity implements a physics-based modelling hierarchy that bridges six length scales:

Scale  |  Method  |  Application in LFP DT  |  Key outputs

Atomistic  |  DFT (VASP/Quantum ESPRESSO)  |  LFP olivine formation energetics, defect energies, Li+ migration barriers  |  Thermodynamic parameters, diffusion coefficients

Molecular  |  Molecular dynamics  |  Carbon coating pyrolysis mechanisms, surface adsorption  |  Carbon coating quality parameters

Mesoscale  |  Phase-field / kinetic Monte Carlo  |  Nucleation and grain growth kinetics during calcination  |  Grain size distribution, phase evolution

Continuum  |  CFD + PBM + reaction kinetics  |  Calcination kiln heat/mass transfer; spray dryer droplet drying; Jander/Avrami reaction kinetics  |  Temperature profiles, conversion rates, particle size evolution

Equipment  |  DEM for jet milling  |  Particle breakage and classification  |  Milled particle size distribution (D50, D90)

Plant  |  Flowsheet simulation (Aspen Plus/gPROMS)  |  Mass/energy balance, throughput optimisation  |  Production rate, energy consumption, yield

The multi-scale chain does not run in real-time at all scales simultaneously. DFT and mesoscale calculations are performed offline to generate material property databases and calibration parameters. These feed into continuum-scale surrogate models (neural network approximations of CFD and PBM solutions, trained on high-fidelity simulation datasets) that execute in real-time (<1 second inference) for closed-loop control [CLM-018]. This surrogate-based hierarchy is the approach validated by TwinHeat for furnace control (achieving <1 C prediction accuracy [CLM-016]) — here extended to chemical powder synthesis for the first time.

Real-time ISO 23247 Layer 4 process twin: The DT implements the ISO 23247 four-layer architecture mapped onto the 7-step LFP CAM production line [CLM-008]:

• Layer 1 (OME): Physical production equipment instrumented with PAT sensors at each process step

• Layer 2 (DCDC): OPC-UA/MQTT data exchange, edge computing nodes (latency <100 ms), PLC/SCADA integration

• Layer 3 (Core DT): Physics-informed surrogate models for each unit operation; multi-fidelity uncertainty quantification; state estimation combining sensor data with model predictions via ensemble Kalman filtering

• Layer 4 (User Entity): Model-predictive control (MPC) for calcination temperature profile, spray drying parameters, and milling energy; quality prediction dashboards; predictive maintenance

Closed-loop MPC using physics-based + ML hybrid models: The MPC controller operates on a receding-horizon optimisation that minimises a cost function combining product quality deviation (from CQA targets), energy consumption, and throughput. The controller receives real-time sensor data, updates state estimates through the physics-informed surrogate, and computes optimal setpoint trajectories for the next control horizon (5-15 minutes for calcination, 1-3 minutes for spray drying).

PAT integration: The DT ingests data from in-line and at-line sensors deployed across the production chain [CLM-019]:

Sensor  |  Measurement  |  Location  |  Update rate

Raman spectroscopy  |  Olivine phase (950 cm-1), carbon D/G ratio, impurities  |  Post-calcination (at-line)  |  30-60 sec

FBRM (focused beam reflectance)  |  Chord length distribution  |  Milling, slurry  |  2 sec

Laser diffraction  |  D10/D50/D90  |  Post-milling (at-line)  |  60 sec

Pyrometry (ratio pyrometer)  |  Temperature  |  Calcination kiln  |  0.1 sec

IR camera  |  Temperature field (2D)  |  Kiln exit, spray dryer  |  10 Hz

Zirconia O2 sensor  |  pO2 (<10 ppm)  |  Calcination kiln atmosphere  |  1 sec

NDIR  |  CO2, CO, CH4  |  Kiln exhaust  |  1 sec

XRF  |  Elemental composition (Li, Fe, P)  |  Post-milling (at-line)  |  5 min

Expected outcomes: Based on cross-industry DT benchmarks validated across steel, chemicals, pharmaceuticals, and battery cell production [CLM-007]:

• Scrap rate reduction: 10-50% (Fraunhofer FFB demonstrated 10.3% in battery cell production [CLM-017])

• Energy consumption reduction: 12-15% (TwinHeat demonstrated 10-15% in furnace operations [CLM-016])

• Batch-to-batch variability reduction: >40%

• Unplanned downtime reduction: 20-50%

Innovation Pillar 2: Progressively Electrified LFP CAM Manufacturing [NOV-002]

Defensibility score: 7/10

What is new: The first LFP CAM production plant designed with a progressive electrification strategy — achieving a 66.6% electrification rate at entry into operation, with 3,580 kWh/t delivered electrically and 189 m3/t of natural gas (1,796 kWh_th/t, 33.4% of total process energy) retained for process steps where full electrification is not yet technically feasible at scale. Total process energy is 5,376 kWh/t. This achieves a significantly higher degree of electrification than the fully gas-fired Asian benchmark, and the plant architecture is designed to accommodate further gas-to-electric substitution as technology matures and Italy's grid decarbonises. The digital twin plays a central role in optimising the energy mix and identifying opportunities for progressive gas elimination.

Electrification roadmap:

Phase  |  Electrification Rate  |  Gas Use (m3/t)  |  Key Change

Entry into Operation (Y0)  |  66.6%  |  189  |  Baseline design

Year 3  |  ~75%  |  ~130  |  HTHP for partial spray drying preheat

Year 5  |  ~85%  |  ~80  |  Extended HTHP coverage + electric kiln optimisation

Year 10 (target)  |  >95%  |  <25  |  Full electric calcination, residual gas for backup only

Note on GHG scoring: Per the Innovation Fund GHG emission avoidance methodology, the project is classified as ES / Manufacturing of Components (Section 1.3.2), where LFP CAM constitutes a specialised battery-grade cathode material — a "component" as exemplified in the methodology. The manufacturing plant itself is outside the GHG calculation system boundary. The GHG avoidance for scoring purposes is calculated based on the use phase of the BESS systems in which the manufactured LFP CAM is deployed — specifically, BESS displacing fossil fuel peaking plants on the Italian electricity grid. The reference scenario is conventional electricity generation from gas peaking plants (CCGT or OCGT). The vertically integrated value chain (LFP CAM to cells to BESS to grid via the co-located JV factory and Eni deployment) provides direct traceability from CAM production to grid-deployed GHG avoidance. The progressive electrification of the plant is therefore an innovation and replicability strength (reducing the product carbon footprint and positioning the plant for long-term competitiveness), but it is not the basis of the GHG avoidance calculation under Section 2.

Electrified calcination: Electric roller hearth kiln (RHK) operating at 700-800 C under flowing N2 atmosphere, with calcination performed in saggars (consistent with roller hearth or pusher kiln configurations). The electric RHK achieves 95% thermal efficiency versus 25-60% for gas-fired rotary kilns [CLM-023, SRC-ED-009]. Electric heating provides superior temperature uniformity (critical for phase-pure olivine formation), eliminates combustion gas contamination of the inert atmosphere, and enables zone-by-zone temperature profile control compatible with DT-driven MPC optimisation. The electric RHK is the established industrial standard for NMC CAM calcination at temperatures to 950 C [SRC-ED-010, SRC-ED-023]; LFP calcination at 700-800 C is well within the proven operating envelope. The initial plant configuration retains some natural gas use (contributing to the 189 m3/t total gas consumption), particularly for auxiliary heating and drying stages where full electrification requires further technology maturation. The DT will optimise the balance between electric and gas heating to minimise both emissions and cost, while guiding the transition pathway toward full electrification.

Heat pump-assisted spray drying: High-temperature heat pump (HTHP) for spray dryer air pre-heating, achieving COP 3.04 at 120 C (Zuhlsdorf et al., 2017 [SRC-ED-004]) to COP 3.6 at 200 C (Zhao et al., 2024 [SRC-ED-005]). This means each kWh of electricity delivers 3.0-3.6 kWh of thermal heat for drying — a 2-3x thermodynamic advantage over direct electric resistance heating and a ~5-10x advantage over gas combustion when accounting for gas-fired dryer efficiency losses [SRC-ED-001]. Final drying stages use direct electric resistance or near-infrared (NIR) heating to reach the outlet temperatures required for complete solvent removal [SRC-ED-019].

GHG and carbon footprint context: The progressive electrification design is framed as a future-proof infrastructure investment. The 66.6% electrification rate achieved from day one is already substantially higher than the fully gas-fired Asian benchmark, and the plant architecture supports continued gas elimination over time. Note: per Section 1.3.4 of the Innovation Fund GHG methodology, the GHG avoidance for scoring purposes is calculated on the use phase of the manufactured battery components, not on the manufacturing plant itself. The electrification trajectory below therefore represents the plant's carbon footprint advantage — a key innovation and replicability differentiator — rather than the scored GHG avoidance metric:

Year  |  Italy grid intensity (gCO2/kWh)  |  GHG reduction vs gas-fired benchmark  |  Basis

2025 (current)  |  ~310  |  Marginal (~5-15%)  |  ISPRA/Nowtricity [SRC-ED-016]

2028 (breakeven)  |  ~180  |  ~30-40%  |  NECP trajectory [SRC-ED-017]

2030 (NECP target)  |  ~146  |  55-70%  |  Italy NECP, 65% renewables [CLM-026]

2035 (G7 commitment)  |  ~30-60  |  80-90%  |  G7 2035 decarbonised power [CLM-026]

The plant enters operation approximately 2028-2029, precisely when the Italian grid crosses the gas-breakeven threshold. Over the plant's 20+ year operational life, cumulative GHG avoidance accelerates as the grid continues to decarbonise [CLM-030]. Electrifying now avoids the capital cost of gas infrastructure that would become stranded assets within 5-7 years of installation.

Electricity as the dominant GHG lever for LFP: Lin et al. (2024) demonstrated that electricity consumption accounts for 39.7% of total global warming potential in LFP battery manufacturing — the single largest contributor [CLM-024, SRC-ED-015]. Switching to clean electricity is the most impactful single decarbonisation intervention, more effective than recycling or chemistry changes. Degen and Schutte (2021, 114 citations) showed that switching from gas+electricity to low-carbon electricity reduces battery cell GHG from 4.54 to 0.53 kgCO2eq/kWh — an 88% reduction [SRC-ED-013].

NMC CAM energy analog: No published LFP-specific industrial CAM synthesis energy data exists [CLM-028]. The best available analog is NMC CAM production at approximately 4 kWh/kg via co-precipitation + calcination (Ahmed et al., 2017, 168 citations [SRC-ED-011]). LFP CAM specific energy is estimated at 3-6 kWh/kg based on this analog and the lower calcination temperature (700-800 C versus 750-950 C for NMC). The project will generate the first primary LFP-specific energy data, addressing this documented research gap [CLM-021].

Cross-industry DT quantitative benchmarks: The projected performance improvements are grounded in demonstrated results across process industries, summarised by the deep-dive report [SRC-DT-REPORT, CLM-007]:

Industry  |  Application  |  Scrap/waste reduction  |  Energy savings  |  Source

Battery cell production  |  Fraunhofer FFB DiBaZ  |  10.3% scrap reduction  |  —  |  [CLM-017]

Industrial furnaces  |  TwinHeat (MINES Paris)  |  —  |  10-15% energy  |  [CLM-016]

Steel production  |  Tata Steel DT  |  —  |  Cumulative savings >$1.4B  |  [SRC-DT-REPORT]

Chemical reactors  |  BASF  |  20-30% unplanned downtime reduction  |  5-8% energy  |  [SRC-DT-REPORT]

Pharmaceutical mfg  |  Various PAT implementations  |  50% out-of-spec batch reduction  |  —  |  [SRC-DT-REPORT]

The FAAM-ENI project targets the conservative end of these ranges (10-50% scrap reduction, 12-15% energy savings) recognising that LFP CAM synthesis is a new domain for DT deployment. These targets will be validated through progressive refinement during commissioning and the first year of operation.

Innovation Pillar 3: ISO 23247 + Multi-Scale Modelling for Chemical Manufacturing [NOV-003]

Defensibility score: 7/10

What is new: The first implementation of the ISO 23247 four-layer digital twin architecture for a thermal/chemical powder synthesis process, combined with a multi-scale physics-based modelling hierarchy spanning atomistic to plant scale.

All existing ISO 23247 implementations address discrete manufacturing — CNC machining [SRC-007, SRC-009], automotive body shop inspection [SRC-010], additive manufacturing [CLM-008]. Discrete manufacturing involves deterministic, geometry-driven operations where the DT models primarily represent kinematics, forces, and dimensional tolerances.

LFP CAM synthesis is fundamentally different: it is a chemical process involving thermally driven solid-state reactions, multi-phase transformations, atmosphere-dependent redox chemistry, and stochastic particle formation. The ISO 23247 framework must be extended to accommodate:

• Reaction kinetics feedback: Real-time tracking of multi-step solid-state reactions (Jander diffusion, Avrami nucleation, shrinking core) with activation energies ranging from 65-180 kJ/mol across decomposition, intermediate formation, olivine crystallisation, and carbon coating steps [CLM-020]

• Atmosphere control: pO2 monitoring and control at <10 ppm under flowing N2 — a safety-critical parameter where deviation causes irreversible Fe3+ surface oxidation and capacity loss

• Multi-phase transformations: Tracking the evolution from amorphous precursor mixture through intermediate phases (Li3Fe2(PO4)3, Fe2O3) to phase-pure olivine LiFePO4, with impurity phases (Li3PO4, Fe2P) as indicators of over-temperature excursions

• Stochastic particle dynamics: Population balance modelling of particle size distributions through spray drying (droplet formation, drying kinetics) and jet milling (breakage, classification), where the DT must predict distributions rather than deterministic states

This extension of ISO 23247 from discrete to chemical manufacturing is a generalisable contribution. The reference architecture developed for LFP CAM is directly applicable to other thermal/chemical powder processes (NMC CAM, anode materials, ceramic powders, pharmaceutical granulation), creating a replicable framework with broad impact beyond this specific project.

The multi-scale modelling chain bridges DFT-derived parameters through to plant-scale flowsheet optimisation. At each scale transition, the higher-fidelity model provides calibration data, material properties, or reduced-order surrogate models to the next level. The computational strategy ensures real-time capability: DFT and mesoscale simulations are performed offline (hours to days per run) to populate material property databases; continuum-scale CFD/PBM/reaction models are trained into neural network surrogates (millisecond inference); plant-scale optimisation uses these surrogates within the MPC framework.

Innovation Pillar 4: Pharmaceutical QbD/PAT for Battery CAM [NOV-005]

Defensibility score: 6/10

What is new: The first formal application of the ICH Q8-adapted Quality-by-Design (QbD) and Process Analytical Technology (PAT) framework to LFP cathode active material manufacturing, establishing systematic CQA-CPP linkages with in-line/at-line monitoring.

The pharmaceutical industry has spent two decades developing and validating the QbD approach under ICH Q8-Q11 guidelines: defining a Quality Target Product Profile (QTPP), identifying Critical Quality Attributes (CQAs), mapping Critical Process Parameters (CPPs), establishing a design space through systematic experimentation, and deploying PAT for real-time quality assurance. This framework has never been formally applied to battery CAM manufacturing [SRC-028, CLM-013, SRC-DT-REPORT].

LFP-specific CQA-CPP mapping: The project establishes the following systematic linkages:

CQA  |  Target  |  Primary CPPs  |  Monitoring

D10 particle size  |  0.3-1.0 um  |  Milling: air pressure, classifier speed  |  Laser diffraction (at-line)

D50 particle size  |  0.7-2.5 um  |  Spray drying: inlet/outlet T, feed rate, nozzle pressure; Milling: air pressure, classifier speed  |  FBRM (in-line), laser diffraction (at-line)

D90 particle size  |  2.5-12.0 um  |  Milling: classifier speed, sieve aperture  |  Laser diffraction (at-line)

Specific surface area (SSA)  |  10-14 m2/g  |  Calcination: T profile, dwell time; Spray drying: droplet size  |  BET (at-line)

Phase purity (olivine)  |  >98%  |  Calcination: T (max 700 C), pO2 (<10 ppm), dwell time  |  Raman (at-line), XRD (at-line)

Carbon content  |  1.0-1.8 wt%  |  Glucose loading (Step 1), calcination T profile  |  Raman D/G ratio (at-line), elemental analysis

Fe2+/Fe3+ ratio  |  >0.95  |  Calcination: pO2 control, cooling rate  |  Mossbauer or XPS (at-line)

Discharge capacity (0.1C)  |  >=155 mAh/g  |  All above (integrated quality)  |  Electrochemical testing (off-line), DT prediction (real-time)

Discharge capacity (1C)  |  >=140 mAh/g  |  All above (integrated quality)  |  Electrochemical testing (off-line)

ICE  |  ~98%  |  Calcination: T profile, atmosphere; Carbon coating quality  |  Electrochemical testing (off-line)

Moisture  |  <750 ppm  |  Packaging: N2 environment, sealing  |  Karl Fischer (at-line)

Magnetic impurities  |  <=1000 ppb  |  Demagnetisation field strength, milling media quality  |  Magnetic susceptibility (at-line)

Tap density  |  1.0-1.4 g/cm3  |  Spray drying: morphology control; Milling: classification  |  Tap density (at-line)

Pellet density  |  >=2.40 g/cm3  |  Calcination: sintering control; Particle morphology  |  Density measurement (at-line)

Electrode press density  |  >=2.30 g/cm3  |  Particle morphology, PSD control  |  Press density measurement (at-line)

Particle morphology  |  Spherical, minimal aggregation  |  Spray drying: T, feed concentration  |  SEM/image analysis (off-line), DT prediction

The QbD framework transforms LFP CAM manufacturing from recipe-based empirical control to model-predictive design-space control. Instead of fixing process parameters and testing the result, the DT continuously predicts product quality from current process state and adjusts parameters to maintain operation within the validated design space. This is the conceptual leap that pharmaceutical manufacturing achieved with PAT — now applied to battery materials for the first time.

Sensor challenges and mitigation: Direct transfer of pharmaceutical PAT to LFP calcination faces practical constraints: Raman probes require sapphire windows that foul at 700-800 C; FBRM cannot survive calcination temperatures; O2 sensors drift at high temperature [SRC-DT-REPORT]. The project addresses these through a hybrid in-line/at-line strategy: true in-line monitoring where sensors can operate (spray drying, milling, packaging) and rapid at-line sampling with automated transfer for calcination-related CQAs (phase purity, carbon quality). The DT's virtual sensing capability bridges the gaps — physics-based models predict calcination-stage CQAs from measurable in-line parameters (temperature, atmosphere, time), validated against periodic at-line measurements.

Mandatory Innovation Dimensions

The Innovation Fund evaluation requires evidence of innovation across plant design, operating approach, construction, performance/quality, reliability/availability, maintenance, and economics. The following table maps the project's innovations to each dimension:

Dimension  |  Innovation beyond SOTA  |  Evidence

**Plant design**  |  Progressively electrified thermal processing (HTHP + electric RHK, with pathway to full electrification); ISO 23247 DT architecture integrated from design phase; PAT sensor network embedded in process equipment; 4 modular lines x 12.5 kton/yr for 50 kton/yr total capacity  |  No existing LFP CAM plant uses electrified process heat or integrated DT [CLM-005, GAP-003]

**Operating approach**  |  Closed-loop MPC replacing recipe-based control; real-time quality prediction from physics-based surrogates; automated process adjustment within design space  |  Current SOTA: empirical, recipe-based, offline QC [CLM-013, SRC-028]

**Construction**  |  Brownfield conversion of Eni industrial site; accelerated timeline leveraging existing infrastructure and permitting precedent  |  Site-specific advantage enabling FC within 2 years, EiO within 4 years

**Performance/quality**  |  Target CQAs: D50 0.7-2.5 um, SSA 10-14 m2/g, >=155 mAh/g capacity (0.1C), >=140 mAh/g (1C), >98% olivine purity, carbon 1.0-1.8 wt%, ICE ~98%; achieved through DT-driven process control  |  DT benchmarks: 10-50% scrap reduction [CLM-007, CLM-017]

**Reliability/availability**  |  Predictive maintenance via DT (20-50% unplanned downtime reduction); condition-based equipment monitoring; virtual sensing for inaccessible parameters  |  Cross-industry DT downtime reduction demonstrated [CLM-007]

**Maintenance**  |  Condition-based monitoring replacing calendar-based schedules; DT-derived equipment health indicators; degradation prediction for heating elements, sensors  |  TwinHeat predictive maintenance for furnace elements [CLM-016]

**Economics**  |  Reduced scrap and energy costs; quality consistency enabling premium pricing; lower total cost of ownership for electrified vs gas equipment (no fuel price volatility)  |  Energy savings 12-15% [CLM-007]; thermal efficiency advantage 1.6-3.8x [CLM-023]

TRL Progression

Component  |  Start TRL  |  End TRL  |  Evidence for current TRL  |  Advancement pathway

LFP solid-state synthesis  |  7  |  9  |  Established industrial route used by all major Chinese producers [SRC-011, SRC-022]. The project's technology licensor, Zhejiang Youshan New Material Technology Co., LTD. (hereafter 'Youshan') provides proven process know-how for the solid-state synthesis route, bridging from TRL 7 (demonstrated industrial route) to the specific Brindisi plant configuration.  |  Process qualification at Brindisi; product certification with cell manufacturers

Electrified calcination (electric RHK)  |  5-6  |  7-8  |  Electric roller hearth kilns commercially available (Kanthal, NGK) and validated for NMC at higher temperatures [SRC-ED-009, SRC-ED-010, SRC-ED-023]; not demonstrated for LFP-specific chemistry/atmosphere  |  System integration with LFP process; validation of product quality under electric heating; long-term reliability demonstration

HTHP spray drying  |  5  |  7  |  HTHP demonstrated at COP 3.04-3.6 in peer-reviewed studies [SRC-ED-004, SRC-ED-005]; not integrated with LFP slurry drying  |  Integration with LFP precursor spray drying; scale-up validation; thermal efficiency verification

DT for CAM synthesis  |  3-4  |  6-7  |  Individual physics-based models validated (ARTISTIC for electrodes [SRC-004]; TwinHeat for furnaces [SRC-DT-REPORT]; Ma et al. for sintering [SRC-014]); no integrated LFP CAM DT exists [CLM-005]  |  Model integration; sensor fusion validation; closed-loop MPC commissioning; industrial operation

ISO 23247 for powder manufacturing  |  3  |  6  |  Standard defined and validated for discrete manufacturing only [SRC-007, SRC-009, SRC-010, CLM-008]  |  Extend to chemical/powder processes; validate data exchange; demonstrate real-time capability

PAT/QbD for LFP  |  4  |  7  |  Pharmaceutical PAT mature (ICH Q8-Q11); LFP CQA/CPP mapping documented [SRC-DT-REPORT]; sensor technologies exist individually  |  Formal CQA-CPP validation; design space establishment; RTRT implementation

Barriers to Overcome

Technological barriers:

1. Scaling multi-scale models to real-time: The DFT-to-plant modelling hierarchy requires surrogate models at each scale transition to achieve real-time inference (<1 second). Training accurate surrogates requires extensive high-fidelity simulation campaigns. The risk is that surrogate fidelity is insufficient for closed-loop control — mitigated by the hybrid approach (physics-based + data-driven corrections from sensor data) and progressive refinement during commissioning.

2. Sensor reliability at >600 C: Raman spectroscopy probes face sapphire window fouling during calcination; FBRM cannot operate above its thermal limit; zirconia O2 sensors drift at sustained high temperatures. Mitigation: hybrid in-line/at-line strategy with virtual sensing to bridge measurement gaps; sensor maintenance scheduling informed by DT-predicted degradation rates.

3. DT-process coupling latency: For effective MPC, the sensor-to-actuator control loop must complete within the process time constant. For calcination (thermal time constant ~minutes), this is achievable. For spray drying (droplet drying time ~seconds), edge computing with pre-computed lookup tables from surrogate models is required. Target: <100 ms sensor-to-prediction latency at edge nodes; <5 second prediction-to-actuation for all MPC loops.

4. LFP-specific atmosphere control under electric heating: Maintaining pO2 <10 ppm in an electric roller hearth kiln requires careful sealing and N2 flow design. Gas-fired kilns inherently consume some O2 through combustion; electric kilns must rely entirely on inert gas purging. This is a design engineering challenge rather than a fundamental barrier — electric kilns for NMC operate at even stricter atmosphere requirements.

Economic barriers:

1. Higher CAPEX for electrified equipment: Electric roller hearth kilns and HTHP systems carry higher upfront capital costs compared to gas-fired alternatives. The total cost of ownership (TCO) analysis favours electrification when gas price volatility, carbon pricing (EU ETS), and avoided stranded asset costs are included. The Innovation Fund grant directly addresses this CAPEX barrier.

2. DT development cost: Building and validating the multi-scale modelling framework, sensor network, data infrastructure, and MPC system represents a significant R&D investment that is not recoverable from a single plant. The Innovation Fund co-financing and the replicability of the DT framework to future plants (and other CAM chemistries) justify this investment.

Why This Scale Is Most Appropriate

The proposed scale — a commercial production plant, not a pilot or demonstration unit — is the most appropriate for validating the integrated innovation package because:

1. DT value proposition requires production-scale variability: Digital twins deliver their greatest value by managing process variability that emerges at production volumes and duration. A pilot plant (TRL 5-6) lacks the throughput, batch counts, and operational duration to generate the data required for DT model validation and MPC tuning. Production scale is essential to demonstrate the 10-50% scrap reduction and 12-15% energy savings claimed.

2. Electrification economics are scale-dependent: The thermal efficiency advantage of electric kilns (95% vs 25-60% [CLM-023]) translates to absolute energy cost savings proportional to production volume. At pilot scale, the fixed costs of HTHP and electric RHK infrastructure overwhelm the variable energy savings. Commercial scale is required for economic viability.

3. Strategic autonomy requires production volume: The EU's dependency on Chinese LFP CAM [CLM-001] is not addressed by pilots. The Innovation Fund explicitly targets manufacturing facilities that establish domestic production capacity aligned with NZIA benchmarks. FREYR had targeted 30,000 t/yr [SRC-025], confirming that commercial scale is the expected ambition level.

4. Precedent: The Innovation Fund had previously funded FREYR's 30,000 t/yr facility (EUR 122M), but FREYR subsequently cancelled these plans. FACE would now be the sole Innovation Fund-supported LFP CAM production facility in Europe. This project is positioned at the same ambition level, differentiated by electrification, DT integration, and geographic positioning.

Industrial calcination scale evidence from licensor candidates: Information provided by licensor candidates confirms that industrial calcination processes for cathode active materials inherently benefit from scale. The evolution from 5x3 to next-generation 6x3 rotary hearth kilns exceeding 110 m in length, with capacities reaching up to 25 kton per year per unit, reflects a clear trend toward larger, more integrated systems. These kilns operate with high throughput (up to 620 saggers per hour), multi-row and multi-layer configurations, and continuous operation without shutdown for maintenance. The ability to maintain stringent process conditions — ultra-low oxygen levels (<1 ppm), tight thermal uniformity (+/-10 C), and precise mechanical control of saggar movement — demonstrates that process stability and product quality are achieved through centralised control systems that become more efficient when distributed over higher production volumes. The reduction in specific operating costs (~414 RMB per ton at ~19 kton/year scale) and the consolidation of capacity into fewer, higher-throughput kilns (4 kilns enabling ~50 kton/year plants) illustrate clear economies of scale. These elements confirm that the performance, energy efficiency, and economic viability of LFP calcination are not scale-neutral, but improve significantly as production systems increase in size and throughput.

2. GHG EMISSION AVOIDANCE POTENTIAL

2.1 Absolute GHG emission avoidance

Absolute GHG emission avoidance

Provide the potential absolute GHG emission avoidance (in tCO2) during the 10 years after the project’s entry into operation using the Guidance on the GHG emission avoidance methodology.

Briefly explain how the calculation was made, in particular:

assumptions for the reference scenario

assumptions for the project scenario

any deviations from the GHG emission methodology and justification.

Support the claims with:

detailed calculations using the GHG emission calculator template. Complete all sheets of the calculator.

Please note that the key elements of the monitoring plan must be described  by completing the ‘data traceability’ sections in the ‘reference emissions’, ‘project emissions’, 'conversion factors’, ‘assumptions’, and ‘CC credit’ sheets.

The result of the calculation must also be included in Part C and in the cost efficiency calculation (part of the financial information file). Please ensure the values provided are consistent.

▶ §2.1 Absolute GHG — GHG TEAM

[GHG TEAM TO COMPLETE]

This section (§2.1 Absolute GHG Emission Avoidance) is owned by the GHG TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Absolute GHG avoidance (tCO2) over 10 years after entry into operation

• Classification: ES / Manufacturing of Components (Section 1.3 + Section 4 of GHG methodology)

• System boundary: BESS use-phase displacing fossil peakers on the Italian grid

• Reference scenario assumptions (conventional gas peaking plants)

• Project scenario assumptions (BESS charged from Italian grid, increasingly renewable)

• Cost share of component (CScomponent): fraction of LFP CAM cost in total BESS system cost — subject to ESS JV affiliated-entity analysis

• Use period: 5 years per methodology

• Complete all sheets of the GHG emission avoidance calculator (Energy Storage template) with data traceability

Word count target: see Part B template guidance for this section.

2.2 Relative GHG emission avoidance

Relative GHG emission avoidance

Provide the potential for relative GHG emission avoidance during the 10 years after entry into operation using the Guidance on the GHG emission avoidance methodology.

The result of the calculation must also be included in Part C. Please ensure the values provided are consistent.

▶ §2.2 Relative GHG — GHG TEAM

[GHG TEAM TO COMPLETE]

This section (§2.2 Relative GHG Emission Avoidance) is owned by the GHG TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Relative GHG avoidance (%) over 10 years after entry into operation

• Must be ≥ 50% for CLEAN-TECH-MANUFACTURING topic

• Calculation consistent with absolute avoidance in §2.1

• Include temporal averaging across 10-year operation period

• Reference Italian grid decarbonisation trajectory (2029 → 2038)

Word count target: see Part B template guidance for this section.

2.3 Minimum requirements

Compliance with DNSH TSC criteria for the environmental objective ‘climate change mitigation’

Explain how compliance with the ‘do no significant harm’ technical screening criteria (TSC) set out in Annex II to Delegated Regulations 2021/2139 and/or 2023/2486 will be ensured for the environmental objective ‘climate change mitigation’ and provide an outline of the plan how these criteria will be fulfilled (see Annex 4 of the Call document).

Note:

Where relevant TSCs exist for an economic activity carried out by the project, you must demonstrate that the project meets the relevant quantitative emission limits as well as all other requirements set by the applicable TSC. This may include the need to develop and present in this box additional calculations (not included in the GHG emission avoidance methodology and calculators).

Compliance with DNSH TSC criteria other than ‘climate change mitigation’ must be described in section 4.1 below.

▶ §2.3 DNSH climate mitigation

# Section 2.3 — Minimum Requirements

2.3.1 Compliance with DNSH Technical Screening Criteria for Climate Change Mitigation

The primary economic activity of the FAAM-ENI Circular Energy project is the manufacture of batteries as defined under Section 3.4 of the EU Taxonomy Regulation (Regulation (EU) 2020/852) and its associated Climate Delegated Regulation (Commission Delegated Regulation (EU) 2021/2139).

GHG Methodology Classification: ES / Manufacturing of Components. Under the Innovation Fund GHG emission avoidance methodology, the project is classified as Energy Storage (ES) / Manufacturing of Components per Section 1.3.2. LFP cathode active material is a specialised battery-grade component — consistent with the methodology's examples of manufactured components for energy storage systems. The GHG system boundary therefore encompasses the use phase of the BESS systems in which the LFP CAM is deployed, not the manufacturing plant itself. GHG avoidance is calculated based on BESS displacing fossil fuel peaking plants (CCGT/OCGT) on the Italian electricity grid. The manufacturing plant's own emissions (Scope 1 and 2) fall outside the GHG calculation boundary; the progressive electrification of the plant is an innovation and replicability argument, not the GHG avoidance argument.

Regulatory position: No additional justification required. Section 3.4 ("Manufacture of batteries") is listed in Table 2 of the Delegated Regulation as an economic activity for which no technical screening criteria (TSC) exist for the climate change mitigation objective, and therefore no additional justification of alignment to DNSH for climate change mitigation is required [CLM-022]. This classification applies to the entirety of LFP cathode active material production, which constitutes a critical upstream manufacturing step in the battery value chain. The project's scope — manufacturing LiFePO4 cathode active material from iron phosphate, lithium carbonate, and glucose precursors — falls squarely within the "Manufacture of batteries" activity definition.

This regulatory classification is confirmed in the Innovation Fund Application Guidance, which specifies that activities listed in Table 2 with the status "No TSC, Therefore Not Required" do not require applicants to provide additional evidence of DNSH compliance for climate change mitigation.

Nevertheless, the project's intrinsic climate mitigation credentials are substantial. While no TSC-based justification is mandated, the project design delivers significant climate benefits through two complementary mechanisms:

(a) Progressive electrification of process heat. The Brindisi plant achieves a 66.6% electrification rate at entry into operation, with 3,580 kWh/t delivered electrically and 189 m3/t of natural gas retained for process steps where full electrification is not yet technically feasible at scale. Electric roller hearth kilns achieve 95% thermal efficiency compared to 25-60% for gas-fired equivalents, representing a 1.6-3.8x thermal efficiency advantage [CLM-023]. The plant architecture is designed for progressive gas elimination (targeting >95% electrification by Year 10). As Italy's grid decarbonises under the NECP trajectory (from approximately 310 gCO2/kWh in 2025 to a projected 146 gCO2/kWh by 2030 and approximately 30-60 gCO2/kWh by 2035 under G7 commitments), the product carbon footprint advantage compounds over the plant's 20+ year operational life [CLM-026, CLM-030].

Electricity consumption during LFP battery manufacture is the single largest contributor to climate change impact, accounting for 39.7% of total Global Warming Potential [CLM-024]. By electrifying production and locating within the EU's rapidly decarbonising grid, the Brindisi plant directly addresses the highest-leverage emission reduction opportunity in the LFP supply chain.

(b) Digital twin-driven process optimisation. The integrated ISO 23247-compliant digital twin enables real-time process control, predictive quality monitoring, and energy optimisation across the production chain. Cross-industry evidence demonstrates that digital twins consistently deliver 10-50% scrap reduction and 5-15% energy savings in process industries [CLM-007]. Scrap reduction directly translates to avoided embedded emissions: every rejected batch represents wasted energy, raw materials, and associated upstream Scope 3 emissions. DT-optimised calcination temperature profiles, informed by the TwinHeat approach (demonstrated 10-15% energy reduction in industrial heat treatment furnaces [CLM-016]), further reduce per-tonne energy consumption and associated GHG emissions.

Compliance confirmation: The project complies with the DNSH principle for climate change mitigation. No TSC applies to the manufacture of batteries under Section 3.4, and the project design inherently advances climate mitigation through electrification and DT-optimised resource efficiency.

2.3.2

ETS benchmark emissions

For projects producing products with an EU ETS benchmark, calculate the process emissions after implementation of the project per unit of product (including any credit for carbon capture and storage or utilisation, calculated following the Guidance on the GHG emission avoidance methodology) and compare this with the equivalent EU ETS benchmark(s) applicable at the time of the application and confirm that the project emissions are lower than the EU ETS benchmark emissions.

▶ §2.3 ETS benchmark

ETS Benchmark Emissions

The project produces lithium iron phosphate (LiFePO4) cathode active material — a specialty inorganic chemical product. Under Commission Implementing Regulation (EU) 2021/447 (setting EU ETS benchmark values for the 2021-2025 period, applicable at call opening on 4 December 2025), LFP CAM does not have a directly corresponding product benchmark.

The EU ETS product benchmark system covers 52 products across sectors including cement, steel, aluminium, and basic chemicals. LFP cathode active material — a high-purity electrochemical material produced at relatively low volumes compared to ETS benchmark commodities — is not among the listed benchmark products. The closest potentially applicable categories are:

• Carbon black benchmark (0.954 tCO2/t product): Not applicable. LFP CAM is not a carbon product; carbon coating constitutes only 1.0-1.8 wt% of the final product [CLM-009].

• Chemicals heat benchmark (6.84 GJ/tCO2): While the calcination step consumes thermal energy, LFP CAM production is fundamentally a materials synthesis process with complex reaction kinetics rather than a simple heat-driven commodity chemical process.

Assessment: LFP cathode active material production does not correspond to any EU ETS benchmark product category. The project's process emissions per unit of product are therefore not subject to ETS benchmark comparison requirements under this call.

LFP cathode active material does not have a direct EU ETS benchmark product under Commission Implementing Regulation (EU) 2021/447. The project falls under the ES / Manufacturing of Components category per Section 1.3.2 of the GHG emission avoidance methodology, and the manufacturing plant is outside the GHG system boundary. The GHG avoidance is calculated based on the use phase of the BESS systems in which the manufactured LFP CAM is deployed — specifically, BESS displacing fossil fuel peaking plants on the Italian electricity grid. The vertically integrated value chain (LFP CAM to cells to BESS to grid deployment by Eni) provides direct traceability from component manufacture to use-phase GHG avoidance. Therefore, the ETS benchmark comparison is applied to the downstream ESS application rather than to the CAM manufacturing process itself.

2.3.3 Sustainability of

Sustainability of biomass

For projects using biomass feedstocks, confirm that the biomass used will at least meet the sustainability requirements of the Renewable Energy Directive 2018/2021. The biomass feedstock must either be listed in Part A of Annex IX of the Directive or be certified as low indirect land use change (ILUC)-risk as defined by Commission Delegated Regulation (EU) 2019/807.

For a commitment to be considered credible, provide evidence of an agreement in principle to source the feedstock from one or more producers who are already certified low ILUC-risk, or evidence of an agreement in principle to source the feedstock from one or more producers who have a clear plan to apply for low ILUC-risk certification.

Explain how sustainability will be ensured.

▶ §2.3 Biomass

Biomass

Not applicable. The FAAM-ENI Circular Energy project does not use biomass feedstocks in any stage of the LFP CAM production process. The three primary raw materials are:

1. Iron phosphate (FePO4) — inorganic mineral precursor

2. Lithium carbonate (Li2CO3) — inorganic mineral precursor

3. Glucose (C6H12O6) — used as a carbon source for the conductive carbon coating on LFP particles

While glucose is derived from agricultural sources, its function in the process is as a chemical precursor for carbon coating (pyrolysed at 700-800 C to form amorphous carbon) rather than as a biomass energy feedstock. Glucose constitutes a minor fraction of total input mass (carbon content target: 1.0-1.8 wt% in final product [CLM-009]) and is consumed in the chemical reaction, not combusted for energy generation. The sustainability requirements of Renewable Energy Directive 2018/2001 (Part A of Annex IX, or certified low ILUC-risk per Commission Delegated Regulation (EU) 2019/807) are therefore not applicable to this project.

No biomass is used for energy generation at the Brindisi facility. The majority of process heat is supplied by grid electricity through electric heating elements (resistance heating in roller hearth kilns and spray dryer systems), with limited natural gas use (189 m3/t LFP CAM) retained in the initial configuration for auxiliary heating. The progressive electrification strategy aims to eliminate residual gas use over time.

Compliance confirmation: The biomass sustainability criterion does not apply. No biomass feedstocks are used in LFP CAM production at the Brindisi facility.

#§IMP-ACT-IA§# #@QUA-LIT-QL@# #@MAT-URI-MU@#

3. PROJECT MATURITY

3.1 Technical maturity

Technical maturity — overview

Provide in the sections below a detailed description of the project’s technical maturity, in particular evidence on the degree of technology readiness of the project and the technical feasibility of delivering the expected project outputs within its operational environment, and of the possible technical risks and related mitigation measures. Cover the current state of project development, building on relevant information or documents.

Attach:

feasibility study annex (mandatory)

due diligence reports (if any).

Technical feasibility

Provide a summary of the following information provided in the feasibility study annex:

project description, including:

block flow diagrams (if applicable)

technical and operational requirements

for maritime sector projects: the description of the existing vessel(s) (if applicable) and details on the operational area, shipbuilding location and servicing network

technical maturity, including:

assumptions used for operational characteristics

technology readiness level

process flow diagram(s)

schematic (preliminary) layout(s) and design(s) (including capacities)

mass and energy balances (including before and after the project, if applicable)

volume of the final product(s)

technical assumptions and figures used for the estimation of the GHG emissions avoidance.

▶ §3.1 Technical feasibility

Technical Feasibility

LFP CAM Production Process

The Brindisi plant employs a wet-route solid-state synthesis process comprising seven sequential unit operations, designed to produce battery-grade LiFePO4 cathode active material. The process is described below with reference to the block flow diagrams in the Feasibility Study annex.

Step 1: Raw Material Dosing and Dispersion

The three primary precursors -- iron phosphate (FePO4), lithium carbonate (Li2CO3), and glucose (C6H12O6, carbon source) -- are gravimetrically dosed into a stirred dispersion tank with deionised water. The stoichiometric ratio targets Li:Fe:P = 1.00:1.00:1.00 (molar), with lithium carbonate providing a slight excess (typically 2-5 mol% Li excess) to compensate for volatilisation losses during calcination [SRC-011]. The glucose loading is 5-15 wt% relative to the total solid content, providing the carbon precursor for in-situ carbon coating during calcination [CLM-020, SRC-DT-REPORT]. The resulting aqueous slurry (typically 30-45 wt% solids) is homogenised by high-shear mixing.

Step 2: Bead Milling and Magnetic Particle Removal

The homogeneous slurry is transferred to a horizontal bead mill (bead mill) for particle size reduction and intimate mixing of the precursors. The target particle size after milling is D50 < 5 um, verified by at-line laser diffraction measurement. Following milling, the slurry passes through an electromagnetic demagnetiser to remove ferromagnetic contaminants introduced during milling (iron wear particles from the mill media). Magnetic contamination above 0.1 ppm Fe metallic is a critical defect that can cause internal short circuits in the final battery cell [SRC-DT-REPORT].

Step 3: Spray Drying (ELECTRIFIED)

The milled aqueous slurry is fed to an industrial co-current spray dryer equipped with a rotary atomiser or pressure nozzle system. The spray dryer inlet air is heated to 200-250 C using electric resistance heaters, replacing the conventional natural gas burners used in Asian benchmark facilities [CLM-011, SRC-ED-001]. The outlet air temperature is controlled at 90-120 C. Spray drying transforms the aqueous slurry into a dry, free-flowing solid precursor powder with engineered particle morphology -- spherical secondary particles comprising intimately mixed primary precursors with uniform glucose distribution.

The spray dryer is a critical quality-determining step: inlet temperature, feed rate, atomiser speed, and air flow rate directly control the dried particle size (D50), morphology (sphericity), residual moisture (<2 wt%), and spatial homogeneity of the carbon precursor within the granule [CLM-009, SRC-012, SRC-013]. Electrification of the spray dryer provides superior temperature control precision compared to gas-fired heating (resistance heaters achieve +/-1 C vs. +/-5-10 C for gas burners), which is advantageous for batch-to-batch consistency [SRC-ED-018].

Electric resistance heating elements (Kanthal Tubothal or SiC elements, rated to 1100 C) are commercially proven in industrial spray dryers for ceramics and food processing at comparable throughputs [SRC-ED-009]. The specific thermal energy demand for spray drying of aqueous slurries is approximately 0.70-1.10 kWh per kg of water evaporated, based on data from the Italian ceramics industry operating in the same geographic region [SRC-ED-021].

The plant comprises 4 modular production lines, each rated at 12,500 t/yr, for a total nameplate capacity of 50,000 t/yr (50 kton/yr). Each line includes its own spray dryer train sized to support the line's throughput requirements. The workshop footprint is approximately 161.1 m x 106 m (~17,100 m2).

Step 4: Calcination (ELECTRIFIED -- Key Innovation Step)

The dried precursor powder is loaded into saggars and introduced into the calcination furnace (roller hearth kiln or pusher kiln configuration) via an automated rail/conveyor system. The furnace operates under nitrogen atmosphere (pO2 < 10 ppm) at 700-800 C for 6-12 hours [CLM-020, SRC-011]. Nitrogen consumption is approximately 850 m3 per tonne of LFP CAM product.

Two electrified furnace configurations are under evaluation for the Brindisi plant:

• Electric roller hearth kiln (RHK): The industrial standard for battery cathode active material calcination. Electric heating zones with independent PID control provide uniform temperature distribution across the kiln cross-section. The NGK HD series and equivalent kilns operate to 1500 C with 40%+ energy reduction versus conventional tunnel kilns [SRC-ED-023]. A CFD-validated model for electric RHK energy optimisation in NMC CAM calcination has been published (Jo et al., 2025), demonstrating <5% heater control deviation [SRC-ED-010]. This model is directly transferable to LFP calcination at the lower operating temperature of 700-800 C.

• Electric rotary kiln: An alternative for continuous throughput. Electric internally-heated or externally-heated rotary calciners have been demonstrated for cement and lime production [SRC-ED-006, SRC-ED-007, SRC-ED-008]. Kanthal (Sandvik Group) supplies electric heating elements (SiC, Tubothal, Fibrothal) rated to 1100 C for battery cathode kiln applications [SRC-ED-009].

Electric kilns achieve 95% thermal efficiency compared to 25% (gas without heat recovery) to 60% (gas with best-in-class heat recovery), representing a 1.6-3.8x thermal efficiency advantage [CLM-023, SRC-ED-009]. For the same thermal work, an electric kiln uses 37-63% of the fuel energy input of a gas-fired kiln. This efficiency gain reduces both operating cost and GHG emissions per tonne of LFP CAM produced.

During calcination, the following sequential reactions occur with activation energies ranging from 65-180 kJ/mol [CLM-020, SRC-DT-REPORT]:

1. Dehydration and organic decomposition (200-400 C): glucose pyrolysis generates amorphous carbon

2. Carbothermal reduction of Fe3+ to Fe2+ (400-550 C): carbon reduces iron phosphate

3. Olivine crystallisation (550-700 C): nucleation and growth of the LiFePO4 phase (Jander/Avrami kinetics)

4. Carbon coating consolidation (700-800 C): residual carbon forms a 2-5 nm conductive layer on LFP particles

Precise temperature profile control across these stages is the primary determinant of product quality. The nitrogen atmosphere must be maintained at pO2 < 10 ppm to prevent Fe2+ oxidation to Fe3+, which degrades electrochemical performance [SRC-DT-REPORT].

Step 5: Jet Milling

The calcined product is de-agglomerated by jet milling (air-flow grinding). The jet mill uses compressed nitrogen or air to achieve high-velocity interparticle collisions, breaking agglomerates while preserving the olivine crystal structure and carbon coating integrity. The target D50 after jet milling is 0.7-2.5 um.

Step 6: Classification and Demagnetisation

The milled powder passes through an ultrasonic vibrating sieve (typical cut-off 10-20 um) to remove oversized particles, followed by an electromagnetic dry powder separator for removal of any ferromagnetic contaminants introduced during milling. The final D50, span (D90-D10)/D50, and magnetic contamination level are verified by at-line laser diffraction and magnetic susceptibility measurement, respectively.

Step 7: Automated Packaging

Qualified LiFePO4 product is automatically packaged under inert atmosphere (N2 blanketing) in moisture-barrier bags to maintain battery-grade moisture levels (<750 ppm). Each batch is assigned a unique lot number with full traceability to all process parameters and quality data.

Mass and Energy Balance

Mass balance (per tonne of LFP CAM product, from production document):

Input  |  Quantity per tonne LFP CAM  |  Annual at 50 kton/yr

Iron phosphate (FePO4)  |  0.98 t  |  49,000 t

Lithium carbonate (Li2CO3)  |  0.25 t  |  12,500 t

Glucose (C6H12O6)  |  0.010 t  |  500 t

TiO2  |  0.008 t  |  400 t

H3PO4  |  0.006 t  |  300 t

The stoichiometric yield is >95% for the lithium and iron-phosphorus streams; the primary mass loss is CO2 from carbonate decomposition and volatiles from glucose pyrolysis. Water is evaporated during spray drying and recovered; nitrogen carrier gas is recycled after scrubbing.

Energy and utility balance (per tonne of LFP CAM product, from production document):

Utility  |  Quantity per tonne LFP CAM

Electricity  |  3,580 kWh

Production water  |  4 t

Pure water  |  5 t

Natural gas  |  189 m3

Nitrogen  |  850 m3

The two energy-intensive steps are spray drying and calcination, which together account for >80% of total process energy consumption [CLM-024, SRC-ED-014]. The measured electricity consumption of 3,580 kWh/t is consistent with the estimated range of 3-6 kWh/kg from NMC CAM analog data (Ahmed et al., 2017 [SRC-ED-011]). The natural gas consumption of 189 m3/t reflects the initial plant configuration; the progressive electrification strategy aims to reduce and eventually eliminate this gas use through electric alternatives in spray drying and calcination auxiliary heating.

Production capacity: The plant is designed for an annual nameplate capacity of 50,000 tonnes (50 kton/yr) of battery-grade LFP CAM, organised across 4 modular production lines of 12,500 t/yr each. With FREYR's cancellation of its 30,000 t/yr project [SRC-025], this positions the Brindisi facility as the largest planned LFP CAM plant in Europe. The target market is primarily ESS cell manufacturers.

Critical Quality Attributes (CQAs)

The following CQA targets define battery-grade LFP CAM, per the QbD framework developed in the DT deep-dive report [SRC-DT-REPORT, CLM-009]:

CQA  |  Target  |  Specification  |  Measurement Method

D10 particle size  |  0.3-1.0 um  |  Range  |  Laser diffraction

D50 particle size  |  0.7-2.5 um  |  Range  |  Laser diffraction

D90 particle size  |  2.5-12.0 um  |  Range  |  Laser diffraction

Specific surface area (SSA)  |  10-14 m2/g  |  Range  |  N2 adsorption (BET)

Tap density  |  1.0-1.4 g/cm3  |  >1.0 g/cm3  |  ASTM B527

Pellet density  |  >=2.40 g/cm3  |  Min 2.40 g/cm3  |  Compaction measurement

Electrode press density  |  >=2.30 g/cm3  |  Min 2.30 g/cm3  |  Press density measurement

Phase purity (olivine)  |  >98%  |  Min 97%  |  XRD Rietveld refinement

Carbon content  |  1.0-1.8 wt%  |  Range  |  TGA / combustion analysis

Fe2+/Fe3+ ratio  |  >0.95  |  Min 0.90  |  Mossbauer / XPS

Discharge capacity (0.1C)  |  >=155 mAh/g  |  Min 150 mAh/g  |  Half-cell electrochemical testing

Discharge capacity (1C)  |  >=140 mAh/g  |  Min 135 mAh/g  |  Half-cell electrochemical testing

Initial Coulombic Efficiency  |  ~98%  |  Min 96%  |  Half-cell electrochemical testing

Moisture  |  <750 ppm  |  Max 750 ppm  |  Karl Fischer titration

Magnetic impurities  |  <=1000 ppb  |  Max 1000 ppb  |  Magnetic susceptibility

Digital Twin Architecture

The digital twin is designed according to ISO 23247:2021, the international standard for manufacturing digital twins [CLM-008, SRC-007, SRC-008]. The four-layer architecture maps directly to the Brindisi plant equipment and control systems:

Layer 1 -- Observable Manufacturing Element (OME): The physical plant assets, including the spray dryer, calcination furnace (RHK or rotary kiln), jet mill, classifier, and all QC instrumentation. Each major equipment unit is assigned a unique asset identifier and a digital representation within the twin.

Layer 2 -- Data Collection and Device Control (DCDC): The sensor network and industrial communication layer. Sensors include:

• Temperature: Type K/S thermocouples (contact measurement, +/-1.5 C accuracy) and ratio pyrometers (non-contact, +/-0.5%) for furnace zone monitoring; IR cameras for full-field 2D thermal mapping of crucible beds

• Particle size: FBRM (Focused Beam Reflectance Measurement) probes for in-line monitoring during milling (0.5-2000 um, 2-second update rate); laser diffraction for at-line D10/D50/D90 verification

• Chemical composition: At-line Raman spectroscopy probes simultaneously measuring olivine phase formation (PO4 stretch at 950 cm-1), carbon coating quality (D/G band ratio), and impurity phases [CLM-019, SRC-DT-REPORT]

• Atmosphere: Zirconia O2 sensors (<10 ppm resolution), NDIR analysers for CO2/CO/CH4, QMS for evolved gas analysis during calcination

All sensor data is communicated via OPC-UA gateways to an edge-fog computing layer, with MQTT publish-subscribe messaging for real-time data streaming. Typical edge-to-fog latency is <100 ms [SRC-DT-REPORT].

Layer 3 -- Digital Twin Core Entity: The computational engine comprising:

• Physics-based models: CFD for furnace temperature distribution (COMSOL/OpenFOAM), population balance models (PBM) for particle size evolution during milling, DEM for milling media dynamics, and multi-step Jander/Avrami reaction kinetics for calcination [CLM-018, SRC-DT-REPORT]

• Physics-informed neural networks (PINNs): Reduced-order surrogate models trained on CFD/PBM simulation data, enabling real-time prediction with <1 second latency [SRC-DT-REPORT]

• ML pipelines: Anomaly detection (autoencoder-based, following the Fraunhofer DiBaZ approach [CLM-017]), multivariate SPC, and predictive quality models correlating CPPs to CQAs

• Time-series database: InfluxDB for high-frequency sensor data storage; HDF5/Delta Lake for batch archival and retrospective analysis

Layer 4 -- User Entity: The human-machine interface comprising:

• Grafana real-time dashboards displaying process state, CQA predictions, and control actions

• Model Predictive Control (MPC) operator interface for furnace temperature profile optimisation, milling parameter adjustment, and spray dryer tuning

• Batch quality reports with automatic pass/fail disposition against CQA specifications

• Decision support: recommended parameter adjustments for next batch based on current batch outcomes

Technology Licensor

FIB has secured a technology licensor for the LFP CAM solid-state synthesis process — Zhejiang Youshan New Material Technology Co., LTD. — which provides a critical risk mitigation pathway for scale-up. The technology licensor contributes: (a) proven process recipes and calcination profiles validated at industrial scale; (b) equipment specification guidance for the roller hearth kiln, spray dryer, and milling systems; and (c) commissioning support including process parameter transfer and initial batch qualification protocols. This licensor relationship substantially de-risks R1 (calcination scale-up) and TR5 (product quality consistency) by providing an established process baseline from which the DT-driven optimisation can begin.

DT Development Milestones

The digital twin development follows a structured timeline integrated with the plant construction and commissioning schedule:

Milestone  |  Month  |  TRL Target  |  Deliverable

DT architecture specification  |  M6  |  —  |  ISO 23247 architecture document

Sensor specification + procurement  |  M9  |  —  |  PAT sensor procurement contracts

Calcination CFD model validated  |  M12  |  TRL 4  |  Model validated on vendor test data

PBM for spray drying validated  |  M15  |  TRL 4  |  Particle size prediction within +/-10%

Surrogate model library built  |  M18  |  TRL 5  |  ROM/PINN models for real-time use

Edge computing infrastructure  |  M18  |  —  |  Edge gateways deployed

Layer 2 (DCDC) operational  |  M24  |  —  |  All sensors streaming to DT platform

MPC for calcination demonstrated  |  M30  |  TRL 5  |  Closed-loop temperature control

Layer 3 (Core DT) operational  |  M36  |  TRL 6  |  Full model chain operational

QbD/PAT framework validated  |  M40  |  TRL 6  |  CQA prediction within spec

Full ISO 23247 Layer 4 integration  |  M42  |  TRL 6  |  Dashboard + MPC + quality reports

DT validated on production batches  |  M48  |  TRL 6-7  |  First production data feedback loop

DT optimisation (Year 1-2 operation)  |  M60  |  TRL 7  |  Model calibration with real data

Technical Risks and Mitigation (Summary)

The principal technical risks are described in detail in Section 3.4 (Risk Management). In brief:

• Scaling multi-scale models to real-time: The full CFD + PBM + reaction kinetics chain requires hours of computation for a single calcination cycle. Mitigation: surrogate models (PINNs, neural network emulators) trained on offline simulations provide real-time predictions within <1 second, validated against offline models at commissioning [CLM-016, SRC-DT-REPORT].

• Sensor reliability at >600 C: Raman probes require sapphire windows that may foul at calcination temperatures; FBRM cannot survive >600 C. Mitigation: redundant sensing architecture combining contact sensors (thermocouples) with non-contact sensors (pyrometers, IR cameras); at-line measurement protocols for CQAs that cannot be monitored truly in-line during calcination; virtual sensors (ML-inferred CQA predictions) as backup when physical sensors are offline [CLM-019].

• DT-process coupling latency: Closed-loop MPC requires sensor-to-actuator response within the process time constant. Mitigation: edge computing for time-critical control loops (furnace zone temperature); fog layer for batch-level optimisation; cloud for retrospective analysis and model retraining. The edge-fog-cloud architecture ensures appropriate latency for each control tier [SRC-DT-REPORT].

Due diligence reports (if any)

Describe relevant main conclusions of technical due diligence reports (if any).

▶ §3.1 Due diligence

Due Diligence

Due Diligence Reports

[TO BE COMPLETED: Independent technical due diligence reports to be referenced here if available (e.g., from equipment vendor assessments, independent process review). The Feasibility Study annex serves as the primary technical documentation for this proposal. The production information document provides detailed process and equipment specifications supporting the technical feasibility assessment.]

3.2 Financial maturity

Financial maturity — overview

This section should provide a detailed overview of the financial maturity of the project, focusing on the robustness of the business plan, financing structure and the commitments of the project funders (lenders and shareholders).

Attach:

detailed budget table/relevant costs calculator (‘financial information file’) (mandatory)

business plan annex (mandatory)

detailed financial model (mandatory)

project shareholders financial resources (mandatory)

support to project – project funding support documentation (mandatory)

terms of supply – project contract terms documentation (mandatory)

due diligence reports (if any).

Project business plan

Provide a summary of the following information provided in the business plan annex:

business proposition (product or business concept, targeted market and market potential, commercialisation strategy and market uptake, competitive landscape)

copy the table with the overview of main parameters underpinning the projections for revenues, CAPEX and OPEX

overview of project counterparties and strategy to secure contracts.

▶ §3.2 Business plan — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§3.2 Project Business Plan) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Business proposition: product, targeted market and market potential, commercialisation strategy, competitive landscape

• Table with main parameters underpinning revenue, CAPEX, OPEX projections

• Overview of project counterparties and strategy to secure contracts

• Copy of business plan annex table for revenue/CAPEX/OPEX parameters

Word count target: see Part B template guidance for this section.

Detailed cash flow projections and project profitability

Provide a summary of the following information provided in the business plan annex:

expected project profitability before and after the requested Innovation Fund grant, including a description of the WACC calculation

main results of the sensitivity analysis.

▶ §3.2 Cash flow — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§3.2 Detailed Cash Flow and Profitability) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Expected project profitability before and after Innovation Fund grant (with WACC calculation description)

• Main results of sensitivity analysis

• Summary tied to business plan annex

Word count target: see Part B template guidance for this section.

Financing plan

Provide a summary of the following information provided in the business plan annex:

breakdown and description of funding sources and uses

project financing structure and debt terms (if relevant)

allocation of Innovation Fund grant and any other public funding.

▶ §3.2 Financing plan — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§3.2 Financing Plan) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Breakdown and description of funding sources and uses

• Project financing structure and debt terms (if relevant)

• Allocation of Innovation Fund grant and any other public funding

Word count target: see Part B template guidance for this section.

Project funders and investors commitment

Provide a summary of the following information provided in the business plan annex:

financing parties and their respective funding contribution

degree of advancement in securing funding sources

conditions for final investment decision and milestones to achieve the targeted financial close date.

▶ §3.2 Funders commitment — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§3.2 Project Funders and Investors Commitment) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Financing parties and their respective funding contribution

• Degree of advancement in securing funding sources

• Conditions for final investment decision and milestones to reach financial close

• Letters of support / commitment from shareholders and lenders

Word count target: see Part B template guidance for this section.

#@CON-SOR-CS@# #@PRJ-MGT-PM@#

3.3 Operational maturity

Operational maturity — overview

In the sections below, provide a detailed description of the operational maturity of the project, demonstrating that the proposed plan for implementing the project is sufficiently developed, comprehensive and realistic.

Attach:

feasibility study annex (mandatory)

due diligence reports (if any), e.g. legal due diligence on intellectual property

permits, licences, authorisations (if any).

Project implementation plan

Describe the implementation planning of the project and key milestones, deliverables and work plan for project development, construction and roll out, and envisaged permitting procedures.

Provide the timeline which must cover the period of the project implementation starting from the signature of the grant up to the end of the monitoring and reporting period and include inter alia the status of project development, the steps concluded so far (e.g. FEED study, initial permits, etc.), the planned date for the final investment decision, start of construction, commissioning and testing, entry into operation.

The timeline should be illustrated in the Gantt chart required in section 9.2.

Provide information on the following aspects:

strategy to reach the milestones of financial close and entry into operation as well as the intermediate milestones

planned timing of project activities and milestones and how it ensures meeting the project milestones (e.g. sufficient time reserve for procurement and delivery of major capital components, commissioning and appropriate ramp-up period of reduced output in the initial operation of the project)

strategy for regular operation of the proposed technology during the monitoring and reporting period (e.g. maintenance, down times for revisions, operational capacities, quality assurance/quality control)

Note: The implementation plan must be consistent with the work packages, milestones and deliverables described in section 9.2.

Applicants are expected to implement the construction works without delay and complete the construction of the project within a reasonable timeframe relative to market standards.

▶ §3.3 Implementation plan

# 3.3 Operational Maturity

3.3a Overview

The FAAM-ENI Circular Energy project is currently at the pre-Final Investment Decision (pre-FID) stage of development. Key project development activities completed to date include: (i) selection and characterisation of the Brindisi brownfield site owned by Eni; (ii) definition of the 7-step LFP CAM production process and preliminary engineering design; (iii) development of the digital twin architecture specification based on ISO 23247 [CLM-008, SRC-007]; (iv) completion of preliminary market analysis confirming EU demand for domestic LFP CAM supply [CLM-001, CLM-003, SRC-023]; and (v) preparation of the present Innovation Fund proposal.

The implementation plan is designed to achieve financial close within 24 months and entry into operation within 48 months of grant agreement signature, targeting the positive scoring consideration for CLEAN-TECH-MANUFACTURING projects that demonstrate accelerated timelines. These targets are achievable given the mature state of the core manufacturing technology (solid-state LFP synthesis at TRL 7-8), the availability of the Brindisi brownfield site with existing industrial infrastructure, and the combined project execution capabilities of FIB (FAAM) and Eni [CLM-022].

Reference: Detailed implementation planning is supported by the mandatory Feasibility Study annex and the Business Plan annex.

3.3b Project Implementation Plan

The implementation timeline covers from grant agreement signature (M0, estimated Q1 2027) through the end of the 5-year operational monitoring period (M108). The plan is structured into two pre-operational phases (WP1: grant to financial close; WP2: financial close to entry into operation) and five operational years (WP3-WP7), consistent with the work package structure described in Section 7.

Key Milestones

Milestone  |  Target Date  |  Month  |  Status  |  Means of Verification

Grant agreement signature  |  Q1 2027  |  M0  |  Planned  |  Signed GA

Detailed project management plan  |  M0+1  |  M1  |  Planned  |  Deliverable D1.1

Final financial model  |  M0+1  |  M1  |  Planned  |  Deliverable D1.2

Knowledge sharing plan  |  M0+1  |  M1  |  Planned  |  Deliverable D1.3

Detailed engineering (FEED) completion  |  Q4 2027  |  M9-M12  |  In preparation  |  FEED report

Environmental permit (VIA) obtained  |  Q1 2028  |  M12-M15  |  Application filed, in process  |  VIA decree

Integrated environmental authorisation (AIA)  |  Q2 2028  |  M15-M18  |  Application filed, in process  |  AIA authorisation

Building permits obtained  |  Q2 2028  |  M15-M18  |  Applications in process  |  Municipal permits

Equipment supplier contracts signed  |  Q3 2028  |  M18-M21  |  Qualification in progress  |  Signed contracts

**Financial close / FID**  |  **Q4 2028**  |  **M21-M24**  |  **Target: within 2 years**  |  **FC documentation package**

Start of construction  |  Q1 2029  |  M24  |  Planned  |  Construction notice

Major equipment delivery and installation  |  Q1-Q4 2029  |  M24-M36  |  Planned  |  Delivery certificates

DT system development (parallel track)  |  M12-M42  |  M12-M42  |  Development initiated  |  Software releases

DT integration and commissioning  |  Q1-Q2 2031  |  M42-M45  |  Planned  |  Integration test reports

Plant commissioning and testing  |  Q2-Q4 2031  |  M45-M48  |  Planned  |  Commissioning certificates

**Entry into operation**  |  **Q1 2031**  |  **M48**  |  **Target: within 4 years**  |  **Operational readiness certificate**

Year 1 GHG monitoring  |  M48-M60  |  M48-M60  |  Planned  |  Annual GHG report

Year 2-5 GHG monitoring  |  M60-M108  |  M60-M108  |  Planned  |  Annual GHG reports

Final reporting and EEA content declaration  |  M108  |  M108  |  Planned  |  Final deliverables package

Phase 1: Grant Agreement to Financial Close (M0-M24)

This phase focuses on advancing project maturity from pre-FID to financial close through four parallel workstreams:

Workstream 1 -- Detailed Engineering: Progression from preliminary design to Front-End Engineering Design (FEED), including: finalisation of process flow diagrams and P&IDs; equipment specification and sizing (spray dryer, calcination furnace, jet mill, classifier, packaging line); site layout and building design for the Brindisi brownfield location; utility requirements (electricity supply, nitrogen generation, water treatment, HVAC); and integration of DT sensor and communication infrastructure into the engineering design.

Workstream 2 -- Permitting: Completion of Italian environmental and construction permitting processes (detailed in Section 3.3d). Early engagement with the Comune di Brindisi and the Regione Puglia environmental authorities has been initiated. Eni's established relationship with local permitting authorities, based on decades of industrial operations at the Brindisi site, is a significant de-risking factor.

Workstream 3 -- Procurement and Supplier Qualification: Identification, qualification, and contracting of critical equipment suppliers (furnace, spray dryer, milling systems, QC instruments, DCS/SCADA systems). Long-lead items (calcination furnace, spray dryer) will be ordered by M18 to support the M24 construction start.

Workstream 4 -- Financing: Finalisation of the project financing structure, equity commitments from FIB and Eni, debt facility negotiation, and execution of all financial close documentation. This workstream is described in detail in Section 3.2 (Financial Maturity).

Phase 2: Financial Close to Entry into Operation (M24-M48)

Construction (M24-M36): Civil works and building construction on the prepared Brindisi brownfield site; installation of utilities, process equipment, and instrumentation; piping, electrical, and control system installation.

DT Development and Integration (M12-M42, parallel track): Development of physics-based models (CFD, PBM, reaction kinetics); training of surrogate models (PINNs); deployment of sensor network and OPC-UA communication infrastructure; integration of models with real-time data pipeline; initial calibration using commissioning batch data.

Commissioning and Testing (M42-M48): Mechanical completion and pre-commissioning checks; utility testing (electricity, N2, water); dry commissioning of individual equipment units; wet commissioning with process materials; production of qualification batches; DT calibration and validation against commissioning data; final CQA verification against battery-grade specifications; operational readiness assessment.

Phase 3: Operational Monitoring (M48-M108)

Year 1 (WP3, M48-M60): Production ramp-up from commissioning rate to nameplate capacity; DT calibration with production-scale data; process optimisation guided by DT insights; annual GHG emission avoidance report.

Years 2-5 (WP4-WP7, M60-M108): Steady-state operation at nameplate capacity; continuous DT model improvement with accumulated production data; annual GHG monitoring and reporting; knowledge sharing activities.

Strategy for Financial Close and Entry into Operation

The project's strategy to achieve the accelerated timelines (FC within 2 years, EiO within 4 years) is based on three pillars:

1. Mature core technology: Solid-state LFP synthesis is at TRL 7-8 with commercially available equipment. No fundamental technology development is required before construction -- the primary risk is process integration and optimisation, not technology feasibility [CLM-011, SRC-ED-009].

2. Brownfield site advantage: The Brindisi site is an existing Eni industrial facility with available land, utility connections (grid electricity, water), transport infrastructure (port and rail access), and established relationships with local authorities. This eliminates greenfield site development time (typically 6-12 months for site acquisition, access roads, utility connections).

3. Strong sponsor commitment and guaranteed offtake: FIB (FAAM) and Eni bring complementary capabilities (manufacturing expertise and site/energy management, respectively) and the financial resources to advance project development in parallel with the Innovation Fund application process. Critically, Eni is the direct internal customer for the LFP CAM output through the co-located ESS (Eni Storage Systems) JV battery cell and BESS manufacturing facility at Brindisi. Eni will deploy the manufactured BESS on the Italian electricity grid, creating a guaranteed offtake pathway that eliminates market risk and secures revenue from entry into operation. This vertically integrated value chain — LFP CAM (this project) to battery cells (JV factory) to BESS (JV factory) to Italian grid deployment (Eni) — massively de-risks the business case and aligns all consortium partners' commercial incentives.

3.3c Due Diligence Reports

[TO BE COMPLETED: Operational due diligence reports (legal, IP, market studies) to be referenced here if available. The market analysis conducted as part of the proposal preparation (see SOTA summary and evidence store) provides the basis for the market positioning argument.]

3.3d Permits, Rights, Licences, and Regulatory Procedures

Permitting Framework

The Brindisi LFP CAM manufacturing plant is subject to the following Italian and EU permitting requirements:

Environmental Impact Assessment (VIA -- Valutazione di Impatto Ambientale): Required under Italian Legislative Decree 152/2006 (Codice dell'Ambiente) for new industrial installations exceeding defined thresholds. The VIA procedure is administered by the Regione Puglia for regional-competence projects or by the Ministero dell'Ambiente e della Sicurezza Energetica (MASE) for national-competence projects. The typical VIA timeline is 12-18 months from application submission to decree issuance. Pre-consultation with the competent authority has been initiated.

Integrated Environmental Authorisation (AIA -- Autorizzazione Integrata Ambientale): Required under the Italian transposition of the EU Industrial Emissions Directive (2010/75/EU) for industrial activities covered by Annex I. The AIA integrates atmospheric emissions, water discharge, waste management, and noise requirements into a single permit. The AIA process is typically conducted in parallel with or following the VIA, with a timeline of 6-12 months.

Building Permits (Permesso di Costruire): Required from the Comune di Brindisi for the construction of industrial buildings and structures. Building permits are contingent on compliance with urban planning instruments (Piano Regolatore Generale) and the area's industrial zoning designation. The Brindisi site is located within an established industrial zone, which is compatible with manufacturing use.

Brownfield Site Status

The Brindisi site is an existing Eni industrial facility. Eni has conducted site characterisation and, where required, remediation activities in accordance with Italian contaminated sites regulations (Title V, Part IV of Legislative Decree 152/2006). The site status is:

The Brindisi site is currently undergoing a brownfield remediation (cleanup) process. The remediation is in progress, confirming the site's brownfield status and Eni's commitment to preparing it for new industrial use. The regulatory clearance status for new construction is being advanced in parallel with the remediation activities, and the permitting applications (VIA, AIA, building permits) are in process.

Intellectual Property

The project leverages commercially available manufacturing equipment, open standards (ISO 23247), and a technology licensor for the LFP CAM solid-state synthesis process. FIB has secured a technology licensor — Zhejiang Youshan New Material Technology Co., LTD. — providing process know-how, recipe optimisation, equipment specification support, and commissioning assistance for the solid-state synthesis route. The licensor relationship is governed by a technology licence agreement covering process recipe transfer, technical support during FEED and commissioning, and ongoing optimisation support. The well-established solid-state chemistry [CLM-014] is complemented by the licensor's proven industrial experience. The LG Chem patent EP2360117B1 on LFP olivine morphology has been assessed and confirmed as non-overlapping with the project's product specification [DEC-005]. The digital twin architecture will be developed as proprietary FIB/Eni intellectual property, with the intent to file patent protection for the novel DT-electrification combination [CLM-015].

Public Acceptance

The Brindisi site is located within an established industrial area with a long history of industrial activity. The project is expected to receive positive public acceptance due to:

• Job creation: Direct employment of [TO BE COMPLETED: FTE numbers for construction and operational phases to be confirmed by HR planning] in the Puglia region, which has above-average unemployment

• Brownfield reuse: Converting an existing industrial site to a high-value advanced manufacturing facility, avoiding greenfield land consumption

• Clean technology alignment: LFP CAM manufacturing for the battery sector aligns with EU and Italian decarbonisation objectives and public support for the energy transition

• No significant negative environmental impacts: The process uses non-toxic raw materials (iron phosphate, lithium carbonate, glucose), operates in a closed system under nitrogen atmosphere, and generates minimal waste streams

Environmental Impacts and Mitigation

The principal environmental impacts of the LFP CAM manufacturing facility and their mitigation measures are:

Impact Category  |  Source  |  Mitigation

Air emissions  |  Spray dryer exhaust (water vapour, trace organics); furnace exhaust (N2, trace CO2/CO)  |  Bag filters + activated carbon adsorption; continuous emissions monitoring

Water consumption  |  Spray drying process water; cooling water  |  Closed-loop cooling; water recycling; rainwater harvesting

Solid waste  |  Off-spec product; spent milling media; packaging waste  |  Off-spec product recycled to process; waste streams classified and disposed per Italian regulations

Noise  |  Milling, material handling, HVAC  |  Acoustic enclosures; site perimeter monitoring

Energy consumption  |  Grid electricity for process heat and equipment  |  Electrified process enables direct GHG reduction as grid decarbonises [CLM-030]

3.3e Project Management Team and Organisation

Beneficiary Structure

The project is implemented as a mono-beneficiary grant application by ESS (Eni Storage Systems) JV, the sole legal beneficiary and coordinator. ESS JV is a jointly owned entity of Eni S.p.A. and FIB S.p.A. (FAAM), both of which provide strategic direction, personnel, technical expertise, and infrastructure through shareholder and intercompany service arrangements.

ESS JV -- Sole Beneficiary and Coordinator

ESS JV is the joint venture company established by Eni and FIB to develop, construct, and operate Italy's first vertically integrated stationary lithium battery platform at the Brindisi site. ESS JV is a registered legal entity in Italy with a validated Participant Identification Code (PIC) in the EU Funding & Tenders Portal. Under its broader industrial plan, ESS JV owns and operates both this LFP CAM plant and the co-located battery cell and BESS manufacturing facility on the same Brindisi site, creating a fully integrated mine-to-grid value chain within a single legal entity. ESS JV's responsibilities include:

• Overall project management and coordination, legal and contractual interface with the Innovation Fund

• LFP CAM process engineering, plant construction, and manufacturing operations

• Quality control and assurance, batch release, regulatory compliance

• Digital twin system specification, development, and operation

• Downstream integration with the co-located cell and BESS manufacturing facility

• Knowledge sharing and dissemination

Eni S.p.A. -- Shareholder (Industrial Partner and Site Provider)

Eni is a global energy company with extensive experience in industrial site management, process engineering, and energy supply. As an ESS JV shareholder, Eni contributes:

• Brindisi industrial site (contributed to ESS JV under the joint venture agreement), including existing infrastructure, utility connections, and permitting precedent

• Seconded personnel: process engineering support (leveraging Eni's refining and chemicals expertise), energy supply architects, environmental management specialists, permitting and stakeholder relations managers

• Balance-sheet strength supporting ESS JV's financial capacity assessment

• Downstream BESS grid deployment: Eni acts as the commercial offtaker for BESS systems manufactured by the ESS JV cell and BESS facility, deploying them on the Italian electricity grid for grid stabilisation and decarbonisation services

FIB S.p.A. (FAAM) -- Shareholder (Battery Manufacturing Expertise)

FIB S.p.A., operating under the FAAM brand, is an Italian battery manufacturer founded in 1974 (Monterubbiano, FM, Italy), a subsidiary of Seri Industrial S.p.A. With approximately 354 employees and over 50 years of experience in lead-acid and lithium-ion battery production, FIB operates Li-ion cell manufacturing at its Teverola site in Caserta (Teverola 1: 300 MWh/year soft pouch cell production in operation; Teverola 2: 8 GWh/year under development) under ISO 9001, ISO 14001, and ISO 45001 management systems. As an ESS JV shareholder, FIB contributes:

• Seconded personnel: battery materials engineers, cell manufacturing specialists, quality control experts, product qualification managers

• Manufacturing know-how transfer from existing Teverola operations

• Established relationships with European battery ecosystem actors and research institutions

• Balance-sheet strength supporting ESS JV's financial capacity assessment

Governance Structure

ESS JV operates under the governance of its shareholders (Eni and FIB), with a joint board of directors appointed by the parent companies. Day-to-day operations are delivered by a mix of directly employed ESS JV staff and personnel seconded from Eni and FIB under intercompany service agreements. Project-level governance comprises three levels:

1. Steering Committee: Strategic decision-making body comprising the ESS JV Managing Director and senior representatives from both shareholders (Eni and FIB). Meets quarterly or as needed for material decisions (scope changes, budget reallocation >10%, risk escalation). Decisions by consensus; escalation to the ESS JV board and ultimately the shareholder boards if needed.

2. Technical Committee: Operational decision-making body comprising the ESS JV Project Manager, Technical Director, Digital Twin Lead, and site/engineering representatives seconded from Eni and FIB. Meets monthly. Responsible for: technical progress review; milestone assessment; risk register updates; and resource allocation.

3. DT Working Group: Specialist body comprising the Digital Twin Lead, DT modelling engineers, sensor integration specialists, and IT/OT infrastructure managers (drawn from ESS JV staff and shareholder secondments). Meets bi-weekly during development phases (M12-M48), monthly during operations. Responsible for: model development progress; data architecture decisions; DT-process integration testing.

Key Roles

All roles below are filled by ESS JV employees or personnel seconded from Eni and FIB under intercompany service agreements.

Role  |  Reporting to  |  Seconded from / Employed by  |  Responsibilities

ESS JV Managing Director  |  ESS JV Board  |  ESS JV / Shareholders  |  Overall leadership, shareholder interface, strategic decisions

Project Manager  |  Managing Director  |  ESS JV  |  Day-to-day project management, reporting to EC/CINEA, work package coordination

Technical Director  |  Project Manager  |  ESS JV (Eni secondment)  |  Process engineering oversight, equipment specification, commissioning management

Digital Twin Lead  |  Project Manager  |  ESS JV (FIB secondment)  |  DT architecture, model development, sensor integration, data pipeline

Quality Manager  |  Project Manager  |  ESS JV (FIB secondment)  |  QC/QA system, CQA monitoring, batch release, regulatory compliance

EHS Manager  |  Project Manager  |  ESS JV (Eni secondment)  |  Environmental, health & safety management, permitting support

Site Manager  |  Technical Director  |  ESS JV (Eni secondment)  |  Brindisi site operations, infrastructure, utility supply, stakeholder relations

Financial Controller  |  Managing Director  |  ESS JV  |  Budget management, cost reporting, audit coordination

Technology Licensor Liaison  |  Technical Director  |  ESS JV  |  Interface with Zhejiang Youshan New Material Technology Co., LTD. for process know-how, recipe optimisation, equipment specification support, commissioning assistance

[TO BE COMPLETED: Specific CVs and track records of named individuals for each role must be provided by the project team and included in the Participant Information annex. The proposal should highlight relevant experience in battery manufacturing, industrial plant construction, and digital manufacturing for each key role.]

Quality Management and Health & Safety

The project will implement quality management in accordance with ISO 9001:2015 and, where applicable, IATF 16949 for automotive-grade battery materials. The quality management system covers: incoming material inspection; in-process quality monitoring (linked to the DT CQA framework); batch release testing; supplier quality management; and traceability (full batch genealogy from raw material lot to packaged product).

Health and safety management follows Italian workplace safety legislation (D.Lgs. 81/2008, Testo Unico sulla Sicurezza) and will be documented in a project-specific Health and Safety Plan. Key H&S considerations include: handling of fine powder (dust explosion prevention, respiratory protection); nitrogen atmosphere operations (asphyxiation prevention, O2 monitoring); high-temperature equipment (burn prevention, thermal insulation); and electrical safety for electrified process equipment.

Due diligence reports (if any)

Describe relevant main conclusions of operational due diligence reports (if any; e.g. legal due diligence on intellectual property, market studies).

▶ §3.3 Due diligence

Due Diligence Reports

[TO BE COMPLETED: Operational due diligence reports (legal, IP, market studies) to be referenced here if available. The market analysis conducted as part of the proposal preparation (see SOTA summary and evidence store) provides the basis for the market positioning argument.]

Permits, rights, licences and regulatory procedures

Provide a summary of the following information provided in the project description section of the feasibility study annex:

intellectual property rights or licence and other relevant regulatory procedures

relevant permitting processes needed (including permits related to environmental impacts), permits obtained and still needed and the plan for obtaining them. Include a timeline indicating the relevant permit application dates, expected reception dates and measures planned to ensure timely granting

degree of public acceptance of the technology and the project and the steps to be taken to ensure public acceptance

main environmental impacts expected throughout the project life-cycle (from construction to operation to decommissioning), and the mitigation measures. Explain when the environmental studies, assessments and modelling will take place.

▶ §3.3 Permits

Permits, Rights, Licences and Regulatory Procedures

Permits, Rights, Licences, and Regulatory Procedures

Permitting Framework

The Brindisi LFP CAM manufacturing plant is subject to the following Italian and EU permitting requirements:

Environmental Impact Assessment (VIA -- Valutazione di Impatto Ambientale): Required under Italian Legislative Decree 152/2006 (Codice dell'Ambiente) for new industrial installations exceeding defined thresholds. The VIA procedure is administered by the Regione Puglia for regional-competence projects or by the Ministero dell'Ambiente e della Sicurezza Energetica (MASE) for national-competence projects. The typical VIA timeline is 12-18 months from application submission to decree issuance. Pre-consultation with the competent authority has been initiated.

Integrated Environmental Authorisation (AIA -- Autorizzazione Integrata Ambientale): Required under the Italian transposition of the EU Industrial Emissions Directive (2010/75/EU) for industrial activities covered by Annex I. The AIA integrates atmospheric emissions, water discharge, waste management, and noise requirements into a single permit. The AIA process is typically conducted in parallel with or following the VIA, with a timeline of 6-12 months.

Building Permits (Permesso di Costruire): Required from the Comune di Brindisi for the construction of industrial buildings and structures. Building permits are contingent on compliance with urban planning instruments (Piano Regolatore Generale) and the area's industrial zoning designation. The Brindisi site is located within an established industrial zone, which is compatible with manufacturing use.

Brownfield Site Status

The Brindisi site is an existing Eni industrial facility. Eni has conducted site characterisation and, where required, remediation activities in accordance with Italian contaminated sites regulations (Title V, Part IV of Legislative Decree 152/2006). The site status is:

The Brindisi site is currently undergoing a brownfield remediation (cleanup) process. The remediation is in progress, confirming the site's brownfield status and Eni's commitment to preparing it for new industrial use. The regulatory clearance status for new construction is being advanced in parallel with the remediation activities, and the permitting applications (VIA, AIA, building permits) are in process.

Intellectual Property

The project leverages commercially available manufacturing equipment, open standards (ISO 23247), and a technology licensor for the LFP CAM solid-state synthesis process. FIB has secured a technology licensor — Zhejiang Youshan New Material Technology Co., LTD. — providing process know-how, recipe optimisation, equipment specification support, and commissioning assistance for the solid-state synthesis route. The licensor relationship is governed by a technology licence agreement covering process recipe transfer, technical support during FEED and commissioning, and ongoing optimisation support. The well-established solid-state chemistry [CLM-014] is complemented by the licensor's proven industrial experience. The LG Chem patent EP2360117B1 on LFP olivine morphology has been assessed and confirmed as non-overlapping with the project's product specification [DEC-005]. The digital twin architecture will be developed as proprietary FIB/Eni intellectual property, with the intent to file patent protection for the novel DT-electrification combination [CLM-015].

Public Acceptance

The Brindisi site is located within an established industrial area with a long history of industrial activity. The project is expected to receive positive public acceptance due to:

• Job creation: Direct employment of [TO BE COMPLETED: FTE numbers for construction and operational phases to be confirmed by HR planning] in the Puglia region, which has above-average unemployment

• Brownfield reuse: Converting an existing industrial site to a high-value advanced manufacturing facility, avoiding greenfield land consumption

• Clean technology alignment: LFP CAM manufacturing for the battery sector aligns with EU and Italian decarbonisation objectives and public support for the energy transition

• No significant negative environmental impacts: The process uses non-toxic raw materials (iron phosphate, lithium carbonate, glucose), operates in a closed system under nitrogen atmosphere, and generates minimal waste streams

Environmental Impacts and Mitigation

The principal environmental impacts of the LFP CAM manufacturing facility and their mitigation measures are:

Impact Category  |  Source  |  Mitigation

Air emissions  |  Spray dryer exhaust (water vapour, trace organics); furnace exhaust (N2, trace CO2/CO)  |  Bag filters + activated carbon adsorption; continuous emissions monitoring

Water consumption  |  Spray drying process water; cooling water  |  Closed-loop cooling; water recycling; rainwater harvesting

Solid waste  |  Off-spec product; spent milling media; packaging waste  |  Off-spec product recycled to process; waste streams classified and disposed per Italian regulations

Noise  |  Milling, material handling, HVAC  |  Acoustic enclosures; site perimeter monitoring

Energy consumption  |  Grid electricity for process heat and equipment  |  Electrified process enables direct GHG reduction as grid decarbonises [CLM-030]

Project management team and project organisation

Describe the project management team and the project organisation, including:

project management team:

project team, including key qualifications and track records of the staff responsible for project implementation (see also participant information)

ability to operate without interruption if a key individual leaves

sufficient coverage of all required skills (such as technical expertise, technology commercialisation, business management, financial management and environmental management)

need for additional outside resources.

project organisation:

project management structure

governance, responsibilities and decision-making mechanisms and processes within the consortium

evidence that the applicant`s management and sponsors are committed to implementing the project

quality management and health and safety processes and how they are expected to meet the best industry practice.

Please make reference to the project diagram provided below.

▶ §3.3 Project management team

Project Management Team and Organisation

Project Management Team and Organisation

Beneficiary Structure

The project is implemented as a mono-beneficiary grant application by ESS (Eni Storage Systems) JV, the sole legal beneficiary and coordinator. ESS JV is a jointly owned entity of Eni S.p.A. and FIB S.p.A. (FAAM), both of which provide strategic direction, personnel, technical expertise, and infrastructure through shareholder and intercompany service arrangements.

ESS JV -- Sole Beneficiary and Coordinator

ESS JV is the joint venture company established by Eni and FIB to develop, construct, and operate Italy's first vertically integrated stationary lithium battery platform at the Brindisi site. ESS JV is a registered legal entity in Italy with a validated Participant Identification Code (PIC) in the EU Funding & Tenders Portal. Under its broader industrial plan, ESS JV owns and operates both this LFP CAM plant and the co-located battery cell and BESS manufacturing facility on the same Brindisi site, creating a fully integrated mine-to-grid value chain within a single legal entity. ESS JV's responsibilities include:

• Overall project management and coordination, legal and contractual interface with the Innovation Fund

• LFP CAM process engineering, plant construction, and manufacturing operations

• Quality control and assurance, batch release, regulatory compliance

• Digital twin system specification, development, and operation

• Downstream integration with the co-located cell and BESS manufacturing facility

• Knowledge sharing and dissemination

Eni S.p.A. -- Shareholder (Industrial Partner and Site Provider)

Eni is a global energy company with extensive experience in industrial site management, process engineering, and energy supply. As an ESS JV shareholder, Eni contributes:

• Brindisi industrial site (contributed to ESS JV under the joint venture agreement), including existing infrastructure, utility connections, and permitting precedent

• Seconded personnel: process engineering support (leveraging Eni's refining and chemicals expertise), energy supply architects, environmental management specialists, permitting and stakeholder relations managers

• Balance-sheet strength supporting ESS JV's financial capacity assessment

• Downstream BESS grid deployment: Eni acts as the commercial offtaker for BESS systems manufactured by the ESS JV cell and BESS facility, deploying them on the Italian electricity grid for grid stabilisation and decarbonisation services

FIB S.p.A. (FAAM) -- Shareholder (Battery Manufacturing Expertise)

FIB S.p.A., operating under the FAAM brand, is an Italian battery manufacturer founded in 1974 (Monterubbiano, FM, Italy), a subsidiary of Seri Industrial S.p.A. With approximately 354 employees and over 50 years of experience in lead-acid and lithium-ion battery production, FIB operates Li-ion cell manufacturing at its Teverola site in Caserta (Teverola 1: 300 MWh/year soft pouch cell production in operation; Teverola 2: 8 GWh/year under development) under ISO 9001, ISO 14001, and ISO 45001 management systems. As an ESS JV shareholder, FIB contributes:

• Seconded personnel: battery materials engineers, cell manufacturing specialists, quality control experts, product qualification managers

• Manufacturing know-how transfer from existing Teverola operations

• Established relationships with European battery ecosystem actors and research institutions

• Balance-sheet strength supporting ESS JV's financial capacity assessment

Governance Structure

ESS JV operates under the governance of its shareholders (Eni and FIB), with a joint board of directors appointed by the parent companies. Day-to-day operations are delivered by a mix of directly employed ESS JV staff and personnel seconded from Eni and FIB under intercompany service agreements. Project-level governance comprises three levels:

1. Steering Committee: Strategic decision-making body comprising the ESS JV Managing Director and senior representatives from both shareholders (Eni and FIB). Meets quarterly or as needed for material decisions (scope changes, budget reallocation >10%, risk escalation). Decisions by consensus; escalation to the ESS JV board and ultimately the shareholder boards if needed.

2. Technical Committee: Operational decision-making body comprising the ESS JV Project Manager, Technical Director, Digital Twin Lead, and site/engineering representatives seconded from Eni and FIB. Meets monthly. Responsible for: technical progress review; milestone assessment; risk register updates; and resource allocation.

3. DT Working Group: Specialist body comprising the Digital Twin Lead, DT modelling engineers, sensor integration specialists, and IT/OT infrastructure managers (drawn from ESS JV staff and shareholder secondments). Meets bi-weekly during development phases (M12-M48), monthly during operations. Responsible for: model development progress; data architecture decisions; DT-process integration testing.

Key Roles

All roles below are filled by ESS JV employees or personnel seconded from Eni and FIB under intercompany service agreements.

Role  |  Reporting to  |  Seconded from / Employed by  |  Responsibilities

ESS JV Managing Director  |  ESS JV Board  |  ESS JV / Shareholders  |  Overall leadership, shareholder interface, strategic decisions

Project Manager  |  Managing Director  |  ESS JV  |  Day-to-day project management, reporting to EC/CINEA, work package coordination

Technical Director  |  Project Manager  |  ESS JV (Eni secondment)  |  Process engineering oversight, equipment specification, commissioning management

Digital Twin Lead  |  Project Manager  |  ESS JV (FIB secondment)  |  DT architecture, model development, sensor integration, data pipeline

Quality Manager  |  Project Manager  |  ESS JV (FIB secondment)  |  QC/QA system, CQA monitoring, batch release, regulatory compliance

EHS Manager  |  Project Manager  |  ESS JV (Eni secondment)  |  Environmental, health & safety management, permitting support

Site Manager  |  Technical Director  |  ESS JV (Eni secondment)  |  Brindisi site operations, infrastructure, utility supply, stakeholder relations

Financial Controller  |  Managing Director  |  ESS JV  |  Budget management, cost reporting, audit coordination

Technology Licensor Liaison  |  Technical Director  |  ESS JV  |  Interface with Zhejiang Youshan New Material Technology Co., LTD. for process know-how, recipe optimisation, equipment specification support, commissioning assistance

[TO BE COMPLETED: Specific CVs and track records of named individuals for each role must be provided by the project team and included in the Participant Information annex. The proposal should highlight relevant experience in battery manufacturing, industrial plant construction, and digital manufacturing for each key role.]

Quality Management and Health & Safety

The project will implement quality management in accordance with ISO 9001:2015 and, where applicable, IATF 16949 for automotive-grade battery materials. The quality management system covers: incoming material inspection; in-process quality monitoring (linked to the DT CQA framework); batch release testing; supplier quality management; and traceability (full batch genealogy from raw material lot to packaged product).

Health and safety management follows Italian workplace safety legislation (D.Lgs. 81/2008, Testo Unico sulla Sicurezza) and will be documented in a project-specific Health and Safety Plan. Key H&S considerations include: handling of fine powder (dust explosion prevention, respiratory protection); nitrogen atmosphere operations (asphyxiation prevention, O2 monitoring); high-temperature equipment (burn prevention, thermal insulation); and electrical safety for electrified process equipment.

Project diagram

Copy the table provided in the business plan with the project diagram (the example below is only an illustrative example and should be deleted when inserting the project specific diagram).

In case a special purpose vehicle is created for the implementation of the project, please specify in the diagram.

Please specify as much as possible the legal and contractual relationships between the main project stakeholders and contractual parties, also including the coordinator and participants mentioned in Application Form Part A.

▶ §3.3 Project diagram — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§3.3 Project Diagram (Copy from Business Plan)) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Copy the project diagram from the business plan annex

• Show legal and contractual relationships between all project participants, including ESS JV shareholders (Eni, FIB), Youshan as technology licensor, and downstream BESS offtake to Eni

• Include any special purpose vehicle arrangements

Word count target: see Part B template guidance for this section.

#§CON-SOR-CS§# #§PRJ-MGT-PM§# #@RSK-MGT-RM@#

3.4 Risk management

Critical risks and risk management strategy

See business plan annex and feasibility study annex.

#§RSK-MGT-RM§# #§MAT-URI-MU§# #§QUA-LIT-QL§# #@IMP-ACT-IA@#

4. REPLICABILITY

4.1 Replicability

Replicability in terms of efficiency gains and multiple environmental impacts

Describe how the project will contribute to efficiency gains and multiple environmental impacts, as described in section 9 of the Call document.

▶ §4.1a Replicability efficiency/environment

Replicability in Terms of Efficiency Gains and Multiple Environmental Impacts

Efficient Use of Critical Raw Materials

The FAAM-ENI Circular Energy project is strategically positioned around LFP chemistry (LiFePO4), which offers fundamental advantages in critical raw material efficiency compared to nickel-cobalt-manganese (NMC) and nickel-cobalt-aluminium (NCA) cathode chemistries that dominate the current European battery supply chain:

Iron and phosphorus abundance. LFP uses iron — the fourth most abundant element in the Earth's crust — as its transition metal, eliminating dependency on cobalt (a conflict mineral with concentrated supply in the DRC) and nickel (subject to significant price volatility and geopolitical supply risk). Phosphorus, sourced as iron phosphate (FePO4), is the binding constraint among LFP feedstocks, but global phosphate rock reserves exceed 70 billion tonnes with diversified geographic supply Iron phosphate consumption is 0.98 t per tonne of LFP CAM (49,000 t/yr at full capacity). Global phosphate rock reserves exceed 70 billion tonnes with diversified geographic supply (USGS Mineral Commodity Summaries).

Lithium efficiency. LFP requires approximately 42 g Li per kWh of cell capacity compared to 50-75 g/kWh for NMC chemistries, representing a 20-44% reduction in lithium intensity per unit of stored energy lithium intensity comparison based on stoichiometric calculations; the Brindisi plant consumes 0.25 t Li2CO3 per tonne LFP CAM (12,500 t/yr at full 50 kton/yr capacity).

Digital twin-driven material yield optimisation. The integrated DT framework directly reduces raw material waste through two mechanisms: (1) predictive quality control reduces scrap rates by 10-50% [CLM-007], meaning fewer rejected batches consuming lithium, iron phosphate, and glucose inputs; and (2) real-time process parameter optimisation via model-predictive control minimises off-specification product that would require reprocessing or disposal. The Fraunhofer FFB demonstrated a 10.3% scrap rate reduction using DT-guided process optimisation in battery cell production [CLM-017] — the FAAM DT extends this approach upstream to CAM synthesis where material losses are proportionally more costly.

Circular Economy and Recyclability

LFP chemistry provides intrinsic circular economy advantages:

Simplified recycling pathway. The absence of cobalt and nickel in LFP eliminates the most complex and environmentally hazardous steps in cathode recycling (selective precipitation of Co/Ni from mixed metal solutions). LFP recycling focuses on lithium recovery — a less technically challenging separation — and iron phosphate recovery for direct re-use as precursor material. This positions the Brindisi plant's output as inherently more recyclable than NMC/NCA alternatives within the emerging EU Battery Regulation recycling framework.

Brownfield site reuse. The project converts an existing Eni industrial site in Brindisi (Puglia) from fossil fuel-related operations to clean-tech manufacturing, directly embodying circular land use principles. No greenfield land is consumed. Existing industrial infrastructure — utility connections, road/rail/port access, wastewater treatment capacity, electrical grid connections — is repurposed, avoiding the embodied carbon and environmental impact of new infrastructure development [CLM-022].

DT-enabled waste minimisation. The digital twin's Quality-by-Design framework systematically maps Critical Quality Attributes (D50 particle size 0.7-2.5 micrometer, SSA 10-14 m2/g, olivine phase purity >98%, carbon content 1.0-1.8 wt%) to Critical Process Parameters [CLM-009], enabling right-first-time production that minimises process waste streams. Batch-to-batch variability reduction (>40% demonstrated in comparable DT implementations [CLM-007]) directly reduces the volume of off-specification material requiring rework or disposal.

Water Management

LFP CAM production via the solid-state spray drying route uses water as a dispersing medium in the slurry preparation stage. The spray drying step evaporates this water to produce dry precursor powder. The Brindisi facility implements a closed-loop water recovery system for the spray dryer: exhaust air from the spray dryer passes through condensation and filtration stages to recover evaporated water for recirculation to the slurry mixing tanks. This closed-loop design reduces freshwater intake by an estimated 70-85% compared to once-through water use water recovery efficiency estimate based on industrial spray dryer condensate recovery systems. The production document specifies 4 t production water and 5 t pure water per tonne LFP CAM; exact recovery rate to be optimised during detailed engineering.

No process water is discharged to surface water or marine environments. All non-recoverable water exits the facility as vapour in exhaust air (after HEPA filtration to remove particulate matter).

Pollution Prevention

The electrified production design eliminates several pollution sources inherent to gas-fired LFP CAM manufacturing:

• Drastically reduced on-site combustion emissions: The progressive electrification strategy achieves a 66.6% electrification rate at entry into operation, minimising natural gas use (189 m3/t in initial configuration versus fully gas-fired benchmark) and dramatically reducing NOx, SOx, CO, and particulate matter emissions. Conventional gas-fired rotary kilns generate approximately 0.5-2.0 kg NOx per tonne of product; the Brindisi plant's limited residual gas use produces a fraction of these emissions, with the electrification roadmap targeting >95% electrification by Year 10 [CLM-011].

• Contained atmosphere processing: Calcination under inert N2 atmosphere (pO2 <10 ppm) prevents formation of Fe2O3 dust and eliminates fugitive iron oxide emissions [CLM-009].

• HEPA filtration: All air handling systems incorporate HEPA filters to capture fine LFP powder (D50 0.7-2.5 micrometer range), preventing release of nano-scale particles to the environment.

• Closed milling systems: Jet milling and ultrasonic sieving operate in enclosed systems with integrated dust collection, preventing fugitive dust emissions.

Biodiversity Protection

The Brindisi site is a designated industrial brownfield within an existing industrial zone. No greenfield conversion is involved. The project does not encroach on protected habitats, Natura 2000 sites, or areas of high biodiversity value. By repurposing an existing industrial site, the project avoids habitat conversion, soil sealing, and ecosystem fragmentation that would accompany a greenfield development. Where remediation of legacy contamination from prior fossil fuel operations is required, this represents a net positive for local environmental quality.

Compliance with DNSH TSC criteria for environmental objectives other than ‘climate change mitigation’

Explain how compliance with the ‘do no significant harm’ technical screening criteria (TSC) set out in Annex II to Delegated Regulations 2021/2139 and/or 2023/2486 will be ensured for the environmental objectives other than ‘climate change mitigation’ and provide an outline of the plan how these criteria will be fulfilled (see Annex 4 of the Call document.

Note:

Compliance with the objective ‘climate change mitigation’ must be described in section 2.3 above.

▶ §4.1b DNSH other objectives

Compliance with DNSH Technical Screening Criteria for Environmental Objectives Other Than Climate Change Mitigation

The DNSH compliance assessment for the five remaining environmental objectives under Regulation (EU) 2020/852 is presented below. Climate change mitigation was addressed in Section 2.3.

1. Climate Change Adaptation

Assessment: The Brindisi facility is located in a coastal Mediterranean industrial zone in Puglia, Southern Italy. The site is exposed to climate change-related risks including increased summer temperatures (projected +1.5-2.5 C by 2050 under RCP4.5), intensified precipitation events, and potential coastal flooding/storm surge amplification.

Mitigation measures:

• Heat resilience: Electric process equipment (roller hearth kilns, spray dryers) operates at design temperatures of 600-800 C and is inherently insensitive to ambient temperature fluctuations of 2-3 C. Building HVAC and DT server room cooling systems are designed with a 3 C safety margin above projected 2050 peak temperatures. Industrial operations are less vulnerable to heat stress than office environments; worker protection follows Italian D.Lgs. 81/2008 occupational heat stress protocols.

• Flood and storm surge resilience: Site engineering incorporates a minimum 0.5 m elevation above the 500-year flood level (including sea level rise projections to 2070). Critical electrical infrastructure (transformers, DT server rooms, control systems) is elevated or flood-protected. Drainage systems are designed for a 1-in-100-year precipitation event with a 20% climate change allowance.

• Supply chain resilience: Raw material storage provides a minimum 30-day buffer stock to mitigate disruption from extreme weather events affecting transport infrastructure. The DT's predictive scheduling module adjusts production planning to accommodate weather-related disruptions.

Compliance confirmation: The project has conducted a proportionate climate risk and vulnerability assessment consistent with Annex A of the Taxonomy Climate Delegated Regulation. Adaptation measures are integrated into the facility design. The project does not increase the vulnerability of surrounding human or natural systems to climate change.

2. Protection of Water and Marine Resources

Assessment: Brindisi is a coastal city on the Adriatic Sea. The industrial zone has existing wastewater treatment infrastructure. LFP CAM production has a relatively low water footprint compared to NMC co-precipitation (which generates significant wastewater streams from washing and pH adjustment steps).

Mitigation measures:

• Closed-loop water system: Spray dryer condensate recovery recirculates process water, reducing freshwater demand by 70-85%. The production document specifies 4 t production water and 5 t pure water per tonne LFP CAM; exact recovery rate to be optimised during detailed engineering.

• Zero industrial discharge: No process wastewater is discharged to surface water, groundwater, or marine environments. Non-recoverable water exits as vapour after HEPA filtration.

• Stormwater management: Site drainage separates clean stormwater from potentially contaminated runoff (e.g., from loading areas). Contaminated runoff is directed to the industrial wastewater treatment system.

• Chemical containment: All liquid chemical storage (lithium carbonate slurry, iron phosphate suspension) is within bunded areas with 110% containment capacity to prevent release to ground or water.

Compliance confirmation: The project does not degrade the status of water bodies or the potential for water bodies to achieve good ecological status. The facility design prevents industrial discharge to water resources.

3. Transition to a Circular Economy

Assessment: The project contributes to circular economy objectives through multiple pathways.

Design for circularity:

• LFP recyclability: The project's output (LFP CAM) is inherently more recyclable than NMC/NCA alternatives due to the absence of cobalt and nickel, which simplify hydrometallurgical recovery processes. LFP recycling enables direct lithium recovery and iron phosphate re-use as precursor.

• Waste minimisation: DT-driven quality control reduces scrap and off-specification production. The QbD framework establishes process design spaces that maximise first-pass yield [CLM-009, CLM-013].

• Process waste streams: Calcination off-gases (primarily N2 + CO2 from glucose pyrolysis) are filtered and vented; no hazardous waste streams are generated. Milling fines below specification are recycled into the slurry preparation stage. Packaging waste (raw material containers) follows standard industrial recycling channels.

• Equipment durability: Electric roller hearth kilns have longer operational lifetimes than gas-fired equivalents (fewer thermal cycling stresses, no combustion-related corrosion), reducing equipment replacement frequency and associated waste.

Compliance confirmation: The project does not lead to significant inefficiencies in the use of materials or in the direct or indirect use of natural resources. The production process is designed to maximise material yield, minimise waste, and produce an inherently recyclable output product.

4. Pollution Prevention and Control

Assessment: LFP CAM production involves handling of fine powders (lithium carbonate, iron phosphate, LFP product) and elevated-temperature processing under controlled atmosphere.

Mitigation measures:

• Air emissions: Minimal on-site combustion (progressively electrified design with residual gas use of 189 m3/t in initial configuration, decreasing over time). HEPA filtration on all powder handling exhausts. Calcination atmosphere is contained (sealed kiln with N2 blanket). No volatile organic compound (VOC) emissions — glucose carbon precursor is pyrolysed under inert atmosphere, not volatilised.

• Chemical safety: All chemicals used (lithium carbonate, iron phosphate, glucose) are classified as low to moderate hazard under CLP Regulation (EC) No 1272/2008. No SVHC (Substances of Very High Concern) or REACH Annex XIV substances are used in the production process. Lithium carbonate requires standard occupational hygiene measures (dust control, PPE) but is not classified as acutely toxic.

• Noise: Electric motors and kilns generate significantly lower noise levels than gas combustion equipment (no combustion roar, no gas valve cycling). Site noise levels at the boundary are expected to comply with Italian DPCM 14/11/1997 industrial zone limits.

• Waste management: No hazardous waste streams are generated. Solid waste (packaging, maintenance consumables, HEPA filters) is managed through licensed industrial waste contractors in accordance with Italian D.Lgs. 152/2006.

Compliance confirmation: The project does not lead to a significant increase in emissions of pollutants to air, water, or land. The progressively electrified design (66.6% at entry into operation, targeting >95% by Year 10) and contained atmosphere processing eliminate the principal pollution sources associated with conventional gas-fired CAM production.

5. Protection and Restoration of Biodiversity and Ecosystems

Assessment: The project is located entirely within an existing industrial zone at Eni's Brindisi brownfield site. No greenfield land conversion is involved.

Mitigation measures:

• No habitat conversion: The site is an existing industrial facility. No natural or semi-natural habitats, agricultural land, or forested areas are affected. No Natura 2000 sites are impacted.

• Brownfield remediation: Where legacy contamination from prior industrial operations exists, the project's site preparation includes remediation to applicable Italian standards (D.Lgs. 152/2006 Parte IV, Titolo V), representing a net improvement in local environmental quality.

• Light and noise: Industrial operations are contained within enclosed buildings, minimising light pollution and noise impacts on surrounding ecosystems. Operating hours and lighting follow standard industrial zone protocols.

Compliance confirmation: The project does not significantly harm biodiversity or ecosystems. The brownfield location ensures zero habitat conversion, and remediation activities provide a net environmental benefit.

Contribution to Europe’s industrial leadership and competitiveness

Describe how the project will contribute to Europe’s industrial leadership and competitiveness, as described in section 9 of the Call document.

For maritime sector projects, describe the contribution of the project in terms of the European added value, as described in the Call document (Glossary).

▶ §4.1c EU industrial leadership

Contribution to Europe's Industrial Leadership and Competitiveness

EU Industrial Ecosystems: Anchoring the European Battery Value Chain

The FAAM-ENI Circular Energy project establishes the first LFP cathode active material production facility in Italy and Southern Europe [CLM-022], directly filling a critical gap in the European battery value chain. As of late 2025, no EU-based company has brought LFP CAM production online [CLM-003], despite LFP being the fastest-growing cathode chemistry globally and the dominant choice for standard-range EVs and grid-scale storage applications.

End-to-End European Battery Value Chain: From Raw Materials to Grid Deployment. The Brindisi plant is not a standalone CAM factory — it is the anchor of a vertically integrated clean energy manufacturing hub that delivers the complete battery value chain within a single consortium and industrial site:

• Upstream: European and allied-nation suppliers of lithium carbonate, iron phosphate, and industrial-grade glucose

• Midstream 1: FAAM Brindisi LFP CAM production (this project) — 50 kton/yr battery-grade cathode material

• Midstream 2: ESS (Eni Storage Systems) JV battery cell and BESS manufacturing facility (co-located at Brindisi) — converting LFP CAM into cells and grid-scale battery energy storage systems

• Downstream: Eni grid deployment — BESS systems deployed on the Italian electricity grid for grid stabilisation and decarbonisation

This mine-to-grid vertical integration is unprecedented in the European battery sector. The co-located JV factory is the direct and guaranteed internal customer for the LFP CAM output. Eni, as the deployer of BESS on the Italian grid, closes the value chain from raw material to grid service. This structure directly addresses the Innovation Fund evaluation criterion regarding "contribution to European industrial ecosystems, integration with strategic energy infrastructure": the project does not merely produce a component — it delivers grid-deployed energy storage that stabilises and decarbonises the Italian electricity system. The integration with Italian grid infrastructure represents a potential connection to Projects of Common Interest (PCI) in the energy storage domain.

The plant also serves external European battery cell manufacturers — including the growing gigafactory ecosystem across Germany, France, Hungary, Poland, and Scandinavia — with domestically produced, EU-traceable LFP cathode material.

The plant's location in Puglia — a Cohesion Policy convergence region — provides geographic diversification within the emerging EU LFP supply map, becoming the sole European LFP CAM production facility following FREYR's cancellation of its Vaasa plans, providing Mediterranean access for Southern European cell manufacturers and export markets.

Reducing EU Dependency on China: Directly Addressing C/2025/3236

This project directly mitigates one of the most acute supply chain dependencies identified by the European Commission. China controls over 99% of global LFP cathode active material production capacity [CLM-001]. Commission Communication C/2025/3236 of 18 June 2025 explicitly identified battery cells, battery packs, and battery materials as products with critical EU dependency on China, requiring urgent mitigation under the Net-Zero Industry Act.

The urgency of this dependency has escalated sharply:

• July 2025: China imposed export licensing requirements on 4th-generation LFP cathode technology, directly restricting technology transfer [CLM-002].

• October 2025: China broadened export controls to include battery cells, precursors, anode materials, and production equipment [CLM-002].

• Strategic implication: The EU battery industry faces a dual risk — dependency on Chinese LFP CAM imports for current production AND dependency on Chinese technology and equipment for any future EU-based LFP CAM manufacturing.

The FAAM Brindisi plant addresses all three dimensions of this dependency:

1. Product supply: Domestic LFP CAM production reduces import dependency for the material itself.

2. Technology sovereignty: The project develops an EU-originated DT-integrated manufacturing process, generating proprietary know-how within the EU/EEA that is not subject to Chinese export control restrictions.

3. Full value chain sovereignty: Through the vertically integrated value chain (CAM to cells to BESS to grid), Italian-made BESS systems are deployed on the Italian electricity grid by an Italian energy company (Eni). This represents complete strategic sovereignty — from raw material processing to grid-deployed energy storage — without any dependency on Chinese technology, components, or deployment infrastructure at any stage of the value chain.

Competitive landscape assessment. FREYR Battery received a EUR 122M Innovation Fund grant for a 30,000 t/yr LFP CAM facility in Vaasa, Finland [CLM-004]. However, FREYR's current corporate strategy prioritises its US Giga America facility. FREYR has stated it is "evaluating options" for its Norwegian and European asset base, and the Vaasa CAM facility has not reached Final Investment Decision (FID). Vaasa competes internally with FREYR's US operations for capital and management bandwidth [CLM-029]. Realistic assessment: FREYR Vaasa is a medium-term option with non-trivial schedule and financing risk — not a near-term locked-in LFP CAM production line. The FAAM Brindisi project, backed by FIB's manufacturing expertise and Eni's industrial site and energy infrastructure, represents the more credible near-term pathway to operational EU LFP CAM capacity.

Building European Know-How: DT Framework as Transferable EU IP

The project generates intellectual property and technical know-how that remains within the EU/EEA:

ISO 23247 reference implementation for chemical manufacturing. The digital twin framework — the first ISO 23247-compliant implementation for thermal/chemical powder synthesis [CLM-008] — constitutes a replicable reference architecture transferable to other EU manufacturers of cathode materials, battery-grade precursors, and advanced ceramic powders. The four-layer architecture (Observable Manufacturing Element, Data Collection & Device Control, Digital Twin Core, User Entity) with its physics-based process models, sensor fusion algorithms, and model-predictive control strategies represents substantial technical IP developed entirely within the EU/EEA.

Multi-scale modeling framework. The integrated modeling chain spanning DFT/atomistic thermodynamics (CALPHAD) through continuum CFD and population balance models to plant-level flowsheet simulation [CLM-018] provides a transferable computational methodology for process optimisation in adjacent EU manufacturing sectors (e.g., catalysts, pigments, functional ceramics, pharmaceutical granulation).

Patent strategy. The core novel combination — electrified spray drying + electric roller hearth kiln calcination with integrated ISO 23247 digital twin for real-time process-quality control for LFP CAM — occupies a patent white space with no identified blocking patent [CLM-014]. The consortium intends to file EU patent applications protecting the DT-integrated electrified CAM manufacturing process, ensuring this IP remains within the EU/EEA.

Vertically integrated model as replicable EU industrial template. Beyond the technology IP, the vertically integrated model itself — co-located CAM production, cell manufacturing, BESS assembly, and grid deployment within a single consortium — represents a replicable industrial architecture for EU battery sovereignty. This model can be replicated at other European brownfield sites where energy companies seek to combine clean-tech manufacturing with grid services, accelerating the EU's transition from component-level manufacturing to integrated clean energy value chains.

Cooperation with EU Research Institutions

The project engages EU/EEA universities and research institutions in the development and validation of the DT framework:

• Italian universities: Collaboration with leading Italian academic institutions for multi-scale modeling development and DT validation. Candidate university partners based on relevant expertise include:

• Politecnico di Milano: A leading European university in digital twin research, hosting the DigiTwin conference and home to the I4.0 Lab and SuPER team (digital twin for chemical engineering). Elisa Negri (recipient of the Digital Twin Young Scientist Award) leads relevant research on manufacturing digital twins.

• Politecnico di Torino: Home to the GAME Lab (Group for Applied Materials and Electrochemistry), with deep expertise in LFP and cathode materials, battery electrochemistry, and nanostructured materials. The GAME Lab maintains active PhD programmes with industrial partners (including Comau and Stellantis), providing a natural framework for collaborative research.

• FIB/FAAM has an established track record of supporting research with universities through PhD studentships and MSc degree collaborations, providing the institutional framework for these partnerships. Specific collaboration agreements to be formalised during WP1.

• EU research networks: Engagement with the EU Battery Alliance ecosystem and relevant Horizon Europe projects for DT methodology cross-fertilisation.

• Standards contribution: The ISO 23247 reference implementation for chemical manufacturing will be documented and contributed to ISO TC 184 (Automation systems and integration) working groups, strengthening EU influence on international manufacturing digitalisation standards.

Capacity Building and Job Creation

The Brindisi facility creates direct employment in Puglia, an EU Cohesion Policy convergence region with high structural unemployment. The project delivers:

• Direct manufacturing employment: Operators, process engineers, quality control technicians, and maintenance staff for the 4-line, 50 kton/yr LFP CAM production facility [TO BE COMPLETED: specific FTE numbers to be provided by FIB HR planning].

• Digital skills development: A dedicated training programme for DT operators — skilled technicians who combine process engineering knowledge with data science and model-based control expertise. This cross-disciplinary skillset is essential for Industry 4.0 manufacturing and currently scarce in Southern Europe.

• Supply chain employment: Indirect job creation through local suppliers of utilities, logistics, maintenance services, and raw material handling.

• Apprenticeship and internship programmes: Structured programmes in partnership with Puglia-region vocational training institutions and universities, building a pipeline of skilled workers for the emerging EU battery manufacturing sector.

Supply Chain Due Diligence

The project implements comprehensive supply chain governance aligned with EU expectations:

• Transparency: EU-based supply chain with full traceability from raw material procurement to finished LFP CAM product. The DT's data architecture (OPC-UA/MQTT, time-series databases, edge-fog-cloud) inherently captures the provenance and process data required for the EU Battery Passport (mandatory from 2027).

• Governance standards: All suppliers are subject to FIB/Eni procurement standards covering governance, anti-corruption, labour rights, and environmental performance.

• Environmental performance: Supplier environmental assessments cover water risk, emissions, waste management, and biodiversity impacts, aligned with the CSRD (Corporate Sustainability Reporting Directive) framework.

• Conflict mineral avoidance: LFP chemistry eliminates cobalt — the battery material most associated with conflict mineral sourcing concerns — removing the single most difficult due diligence challenge in battery supply chains.

• Human and social rights: Lithium sourcing follows EU Critical Raw Materials Act due diligence requirements. Iron phosphate and glucose are sourced from established industrial supply chains with no identified human rights red flags.

EEA-Originating Content

The Brindisi facility is located in Italy (EU Member State). The LFP CAM product is manufactured entirely within the EU/EEA. Key equipment and technology components:

• Manufacturing equipment: Electric roller hearth kilns, spray dryers, jet mills, and ultrasonic sieving equipment sourced from EU/EEA and allied-nation suppliers where available (e.g., Kanthal/Sandvik for electric heating elements — Sweden; NGK or equivalent for roller hearth kiln systems).

• DT infrastructure: Software development, modeling frameworks, and data architecture developed within EU/EEA.

• Process know-how: The integrated DT-electrified manufacturing process is developed entirely within the EU/EEA consortium.

The declaration on equipment/components EEA-originating content (mandatory deliverable in the last year of operation for CLEAN-TECH-MANUFACTURING projects) will be prepared and submitted as part of the final work package.

#@COM-DIS-VIS-CDV@#

4.2 Knowledge sharing — Communication, dissemination and visibility

Knowledge-sharing — Communication, dissemination and visibility of funding

Outline the activities, content, tools, channels and target groups for knowledge-sharing that go beyond the mandatory knowledge-sharing requirements (i.e. reporting and participation in knowledge-sharing events organised by the granting authority; see knowledge-sharing report available on the EU Funding & Tenders Portal Reference Documents for minimum requirements).

These can include but are not limited to: participation and organisation of technical and scientific events, trainings, lectures, participation in work groups and discussion forums, organisation of site visits, construction of a visitors centre, etc.

Describe how the visibility of EU funding will be ensured.

Note: For successful projects, a detailed knowledge sharing plan will have to be provided later on, as deliverable (see section 10 of the Call document).

▶ §4.2 Knowledge sharing

Knowledge Sharing — Communication, Dissemination, and Visibility

The FAAM-ENI Circular Energy project commits to an ambitious knowledge sharing programme that extends beyond mandatory requirements, reflecting the project's strategic importance for EU battery sovereignty.

Technical and Scientific Publications

• Peer-reviewed publications: A minimum of 3 peer-reviewed publications over the project lifetime, targeting journals such as Journal of Power Sources, Journal of The Electrochemical Society, and Computers & Chemical Engineering. Publication topics include: (1) the ISO 23247 reference implementation for chemical powder manufacturing; (2) multi-scale modeling methodology for LFP CAM synthesis; (3) electrified LFP CAM production energy and GHG performance data (the first published LFP-specific data, addressing the research gap identified in CLM-028).

• Conference presentations: Annual presentations at major EU battery and manufacturing conferences (EU Battery Alliance events, The Battery Show Europe, ACHEMA, Digital Twin Conference).

Open-Source DT Framework Components

Where commercially non-sensitive, the project will release open-source components of the DT framework:

• ISO 23247 reference architecture documentation for chemical manufacturing (layer specifications, interface definitions, data schemas)

• Validated surrogate models for generic spray drying and calcination unit operations (without proprietary LFP-specific parameters)

• Data integration templates for OPC-UA/MQTT sensor-to-DT data pipelines

This approach balances IP protection for the consortium with the EU objective of building a shared knowledge base for manufacturing digitalisation.

Site Visits and Stakeholder Engagement

• Annual site visits: The Brindisi facility will host annual site visits for EU battery ecosystem stakeholders, including cell manufacturers, equipment suppliers, policy makers, and research institutions. Visits include production line tours (within IP constraints), DT demonstration, and technical discussion sessions.

• EU Battery Alliance engagement: Active participation in EU Battery Alliance working groups on manufacturing digitalisation and cathode material production.

Training Programmes

• DT operator training curriculum: Developed in partnership with regional vocational institutions, the training programme will be documented and made available as a replicable template for other EU manufacturers implementing digital twin systems.

• Masterclass series: Annual 2-day technical masterclasses on DT-driven manufacturing for industry participants, combining lectures with hands-on simulation exercises using the project's validated models.

Annual Knowledge Sharing Reports

As a mandatory deliverable, knowledge sharing reports will be submitted at each milestone (financial close, entry into operation, annually during operational monitoring). These reports will document:

• Technical progress and lessons learned

• Publications and presentations completed

• Site visits conducted and stakeholder feedback

• Training programmes delivered and participants reached

• Open-source releases and adoption metrics

EU Funding Visibility

All project communications, publications, technical documentation, and site signage will prominently display:

• The EU flag and Innovation Fund logo

• The acknowledgment text: "This project has received funding from the Innovation Fund of the European Union"

• The grant agreement number and project acronym

Visibility measures comply with the grant agreement communication and dissemination obligations and the Innovation Fund branding guidelines.

#§COM-DIS-VIS-CDV§# #§IMP-ACT-IA§# #@FIN-MGT-FM@#

5. COST EFFICIENCY

5.1 Relevant costs and cost efficiency ratio

Relevant costs and cost efficiency ratio

Provide a calculation of cost efficiency ratio: (requested Innovation Fund grant + any additional public support reflected in the financial model / absolute GHG emission avoidance during the first 10 years of operation [EUR / t CO2-eq]).

Attach:

detailed calculation of relevant costs by filling in the financial model summary inputs, CAPEX inputs, RC inputs, to be submitted as part of the financial information file using the required template

cost efficiency calculation to be submitted as part of the financial information file using the required template

the maximum amount of the requested Innovation Fund grant, as part of the financial information file (maximum grant amount cannot exceed 60% of the relevant costs)

Explain how the relevant costs are calculated using the Guidance on the relevant cost methodology and any underlying assumptions used.

If you use the reference plant calculation methodology (Option 2 in the Guidance on the relevant cost methodology), explain

how you meet the conditions for the methodology set out in the guidance

why you chose this methodology.

Note: The requested EU grant should be consistent with the relevant cost calculation.

▶ §5.1 Cost efficiency — FINANCIAL TEAM

[FINANCIAL TEAM TO COMPLETE]

This section (§5.1 Relevant Costs and Cost Efficiency Ratio) is owned by the FINANCIAL TEAM and is pending completion by the Financial / GHG teams as part of the coordinated submission process.

Required content:

• Detailed calculation of relevant costs using the Financial Information File template

• Cost efficiency ratio: (requested grant + any additional public support) / absolute GHG avoidance (tCO2eq over 10 years of operation)

• Confirmation that cost efficiency ratio ≤ 200 EUR/tCO2eq

• Explanation of relevant cost methodology option selected (Option 1 direct, or Option 2 reference plant)

• Maximum requested grant ≤ 60% of relevant costs

Word count target: see Part B template guidance for this section.

#§FIN-MGT-FM§#

6. BONUS POINTS

Bonus points

Where relevant, address one or multiple bonus points indicated in section 9 of the Call document. Clearly substantiate your claims and make reference to other relevant parts of the proposal.

▶ §6 Bonus points

# Section 6 — Bonus Points

Bonus 1: Potential to Deliver Net Carbon Removals

Not applicable. The FAAM-ENI Circular Energy project is an LFP cathode active material manufacturing facility. The project delivers significant GHG emission avoidance through electrification of process heat and DT-driven energy optimisation (detailed in Sections 2.1 and 2.2), but it does not incorporate a mechanism for net carbon removal (negative emissions).

LFP CAM production is a materials synthesis process that consumes lithium carbonate, iron phosphate, and glucose as inputs. While glucose pyrolysis during calcination produces a carbon coating on LFP particles, this carbon originates from a biogenic source and represents a negligible mass fraction (1.0-1.8 wt% of final product [CLM-009]) that is ultimately released at end-of-life recycling — not permanently sequestered. No carbon capture and storage (CCS), direct air capture (DAC), or bioenergy with CCS (BECCS) component is included in the project scope.

The project's climate contribution is through emission avoidance (displacing gas-fired Chinese LFP CAM production with electrified EU production), not through net carbon removal.

Bonus 2: SME-Coordinated and Implemented Project

Not applicable. The project consortium consists of:

• FIB (FAAM) — Coordinator. FIB is a subsidiary within the FAAM group, a large enterprise exceeding the EU SME thresholds (Commission Recommendation 2003/361) for headcount, turnover, and balance sheet total.

• Eni S.p.A. — Beneficiary. Eni is a multinational energy corporation and one of Italy's largest companies, with approximately 32,000 employees and annual revenues exceeding EUR 90 billion.

Neither consortium partner qualifies as an SME. This bonus criterion requires that all beneficiaries and affiliated entities be SMEs, which is not the case.

Bonus 3: Maritime Sector Projects

Not applicable. The FAAM-ENI Circular Energy project manufactures LFP cathode active material for the general battery market (electric vehicles, grid-scale energy storage). While LFP batteries have emerging applications in maritime electrification (e.g., short-sea shipping, port equipment), the Brindisi plant's primary market and production targets are not specifically directed at maritime sector decarbonisation. The project does not meet the requirement for demonstrated potential specifically for decarbonising the maritime sector.

#@WRK-PLA-WP@#

7. WORKPLAN, WORK PACKAGES, ACTIVITIES, MILESTONES, DELIVERABLES AND TIMING

7.1 Work plan

Work plan (overview of work packages, milestones and deliverables)

Provide a brief description of the overall structure of the work plan (list of work packages or graphical presentation (Pert chart or similar)).

List the work packages, their duration (from Month YX to month YX, relative to the starting date of the Innovation Fund project, e.g., Month 01 is the starting month of the project, etc.), and related deliverables and milestones for each work package below. These should be consistent with the detailed work package descriptions in section 9.2.

More work packages, deliverables and milestones can be added by adding rows to the table. Add to each milestone the means of verification of its achievement.

Work package

Duration

Deliverable (continuous numbering linked to WP)

Milestones (continuous numbering not linked to WP) and their means of their verification

Work package 1: [name of the work package]

YX - YX

D1.1, D1.2 ….

MS1, MS2 ……

Work package 2: [name of the work package]

YX - YX

D2.1, D2.2 …..

MSX, MSX+1 …….

…

7.2 Work packages, activities, resources and timing

WORK PACKAGES

Work packages

This section gives a detailed description of the project activities.

Group your activities into work packages. A work package means a major sub-division of the project. For each work package, enter an objective (expected outcome) and list the activities, milestones and deliverables that belong to it. The grouping should be logical and guided by identifiable outputs.

Please respect the following set-up:

your project should include the following sequential work packages (mandatory):

WP1 –  Up to Financial Close

WP2 – Between Financial Close and Entry into Operation

for all (except NZT GENERAL-SSP and PILOTS topics): WP3 – WP7 – Year [1, 2, 3, …] of Operation (annual  reporting during the operation phase)

for NZT GENERAL-SSP and PILOTS topics: WP3 – WP5 – Year [1, 2, 3] of Operation (annual  reporting during the operation phase)

you may define additional work packages by subdividing the above mandatory work packages (e.g. subdivide WP1 Activities prior to Financial Close into two separate WPs: a WP for completion of FEED study or for exploration of the geothermal reservoir, and a WP for financial close, or by subdividing the WP2 Activities between Financial Close and Entry into Operation into more WPs for the construction phase). Please ensure the correct progressive numbering of the work packages and that 3/5 work packages are included for the annual reporting during the operation phase.

You can create as many work packages as needed by copying and adjusting the tables below.

As payments of the grant will be on a lump-sum basis when work packages are completed (prior to entry into operation) and also based on verified greenhouse gas reductions (after entry into operation), you must conclude each work package with a financial reporting milestone specific to that work package. The conclusion of each work package and the reaching of its related financing reporting milestone will open the right to the corresponding lump-sum payment. You must ensure that the budget for each work package including the expected allocation of the lump-sum contribution is proportional to the activities and effort covered by that work package.

Ensure consistency with the detailed budget table/relevant cost calculator (financial information file)

Objectives

List the specific objectives to which the work package is linked.

Activities and division of work (WP description)

Provide a concise overview of the work (planned tasks). Be specific and give a short name and number for each task. For WP1, please also provide an overview of the documents which are typically needed before financial close (for instance signed credit facility agreements, contracts with project stakeholders (e.g. construction, offtake, O&M), FEED study, permit documents, due diligence reports, insurance documents, shareholder agreements and board resolutions).

Show who is participating in each task: Coordinator (COO), Beneficiaries (BEN), Affiliated Entities (AE), Associated Partners (AP), indicating in bold the task leader.

Note:

The Coordinator remains fully responsible for the coordination tasks, even if they are delegated to someone else. Coordinator tasks cannot be subcontracted.

Milestones and deliverables (outputs/outcomes)

Milestones are the main control points in the project that help to chart progress.

You can have several project milestones inside a work package; but you can have only one milestone at the end of the work package which triggers payments.

Each project should have the following minimum reporting milestones triggering payments:

financial close (milestone at the end of WP1)

entry into operation (milestone at the end of WP2)

annual reporting of GHG emission avoidance (milestone at the end of WP3 – WP7/WP3 – WP5 at the end of each annual reporting period during the operation phase of the project)

Means of verification is the evidence in addition to the documents submitted as deliverables which are needed to demonstrate that a milestone has been reached.

Deliverables are project outputs which are submitted to show project progress. Please refer to the main contracts and documents. Do not include minor sub-items, internal working papers, meeting minutes, etc. For each deliverable you must indicate a due month by when you commit to upload it in the Portal. The due month for the deliverable cannot fall outside the work package period and must be in line with the timeline provided below. Month 1 marks the start of the project and all deadlines should be related to this starting date.

The labels used mean:

Public — fully open ( automatically posted online on the Project Results platforms)

Sensitive — limited under the conditions of the Grant Agreement

EU classified — RESTREINT-UE/EU-RESTRICTED, CONFIDENTIEL-UE/EU-CONFIDENTIAL, SECRET-UE/EU-SECRET under Decision 2015/444. For items classified under other rules (e.g. national or international organisation), please select the equivalent EU classification level.

Work Package 1

Work Package 1: Up to Financial Close

Duration:

MX - MX

Lead Beneficiary:

1-Short name

Objectives

Reaching financial close within the timeframe defined in section 6 of the Call document.

Activities and division of work (WP description)

Task No

(continuous numbering linked to WP)

Task Name

Description

Participants

In-kind Contributions and Subcontracting

(Yes/No and which)

Name

Role

(COO, BEN, AE, AP, OTHER)

T1.1

n/a

T1.2

n/a

n/a

Milestones and deliverables (outputs/outcomes)

Milestones: Include as mandatory milestone the one triggering the payment at financial close. Other indicative milestones (depending on specificity of each project) are:

project planning approved; with the following deliverables: FEED study finished; go to market strategy; supply/procurement strategy

project authorisation granted (including permits); with the following deliverables : relevant permits granted (environment, building, operation, public acceptance); land purchase or lease contract signed; final design approved at appropriate level

main project contracting closed; with the following deliverables : signed PPA/off take contract; signed EPC document or construction contract; signed long term service agreement; signed feedstock/supply contract

project financing means granted (final investment decision), with the following deliverables: final investment decision (FID) with signed financing agreements at appropriate level; signed credit facility with confirmation that all drawdown conditions are fulfilled; signed public funding agreement, signed shareholder agreement.

Please adjust the milestones or include other relevant milestones and the corresponding means of verifications, relevant for your project.

Deliverables: Include the mandatory deliverables for this WP listed in section 10 of the Call document. Moreover, add any other essential document to verify the achievement of the financial close and other milestones; these in principle are project specific, however the following are expected to be included as deliverables: final version of the financial model; signed version of the consortium agreement (where applicable); essential financing agreements and project contracts (offtake/feedstock/construction/O&M).

Other non-critical documents can be uploaded as means of verification of the related milestones (see below).

Milestone No

(continuous numbering not linked to WP)

Milestone Name

Work Package No

Lead Beneficiary

Description

Due Date

(month number)

Means of Verification

MS1

1

MS2

1

MS…

Financial Close

1

Milestone triggering payment

All the previous supporting documents and deliverables for this phase, as relevant for the project

Deliverable No

(continuous numbering linked to WP)

Deliverable Name

Work Package No

Lead Beneficiary

Type

Dissemination Level

Due Date

(month number)

Description

(including format and language)

D1.1

1

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

D1…

1

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

Work Package 2

Work Package 2: From Financial Close to Entry into Operation

Duration:

MX - MX

Lead Beneficiary:

1-Short name

Objectives

Reaching entry into operation.

Activities and division of work (WP description)

Task No

(continuous numbering linked to WP)

Task Name

Description

Participants

In-kind Contributions and Subcontracting

(Yes/No and which)

Name

Role

(COO, BEN, AE, AP, OTHER)

T2.1

n/a

T2.2

n/a

n/a

Milestones and deliverables (outputs/outcomes)

Milestones: Include as a mandatory milestone the entry into operation (milestone triggering payment). Other indicative milestones (depending on specificity of each project) are:

site preparation, with relevant reports or evidence as deliverables

construction, with relevant reports or evidence as deliverables

pre-commissioning, with relevant reports or evidence as deliverables

operation and maintenance, with relevant maintenance and operation agreement signed as deliverables

commissioning, start-up and testing, with the following deliverables: commissioning protocol signed by all relevant parties, signed protocol stating the start-up date, procedure and test results; completion certificate.

Please adjust the milestones or include other relevant milestones and the corresponding means of verifications, relevant for your project.

Deliverables: Include the mandatory deliverables for this WP listed in section 10 of the Call document. Moreover, add any other essential deliverable suitable to report on the progress of the WP activities (e.g. operational readiness and completion certificate) and the achievement of the entry into operation.

Milestone No

(continuous numbering not linked to WP)

Milestone Name

Work Package No

Lead Beneficiary

Description

Due Date

(month number)

Means of Verification

MS..

2

MS…

2

MS…

Entry into operation

2

Milestone triggering payment

All the previous supporting documents and deliverables for this phase, as relevant

Deliverable No

(continuous numbering linked to WP)

Deliverable Name

Work Package No

Lead Beneficiary

Type

Dissemination Level

Due Date

(month number)

Description

(including format and language)

D2.1

2

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

D2…

2

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

Work Package 3

Work Package 3: Year 1 of Operation

Duration:

MX - MX

Lead Beneficiary:

1-Short name

Objectives

Achievement of the expected GHG emissions savings.

Activities and division of work (WP description)

Task No

(continuous numbering linked to WP)

Task Name

Description

Participants

In-kind Contributions and Subcontracting

(Yes/No and which)

Name

Role

(COO, BEN, AE, AP, OTHER)

T3.1

n/a

T3.2

n/a

n/a

Milestones and deliverables (outputs/outcomes)

Milestones: Include as mandatory milestone the one triggering the payment at the end of year 1 of operation. Depending on the specificities of your project, please adjust the milestones or include other relevant milestones and the corresponding means of verifications.

Deliverables: Include the mandatory deliverables for this WP listed in section 10 of the Call document, in particular the annual GHG emissions avoidance report. Moreover, add any other essential deliverable suitable to report on the progress of the WP activities and the achievement of the expected GHG emissions savings.

Milestone No

(continuous numbering not linked to WP)

Milestone Name

Work Package No

Lead Beneficiary

Description

Due Date

(month number)

Means of Verification

MS….

3

MS…

End of first year of operation

3

Milestone triggering payment

All the previous supporting documents and deliverables for this phase, as relevant

Deliverable No

(continuous numbering linked to WP)

Deliverable Name

Work Package No

Lead Beneficiary

Type

Dissemination Level

Due Date

(month number)

Description

(including format and language)

D3.1

Annual GHG emission avoidance report

3

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

D3…

3

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

Work Package 4

Work Package 4: Year 2 of Operation

Duration:

MX - MX

Lead Beneficiary:

1-Short name

Objectives

Achievement of the expected GHG emissions savings.

Activities and division of work (WP description)

Task No

(continuous numbering linked to WP)

Task Name

Description

Participants

In-kind Contributions and Subcontracting

(Yes/No and which)

Name

Role

(COO, BEN, AE, AP, OTHER)

T4.1

n/a

T4.2

n/a

n/a

Milestones and deliverables (outputs/outcomes)

Milestones: Include as mandatory milestone the one triggering the payment at the end of year 2 of operation. Depending on the specificities of your project, please adjust the milestones or include other relevant milestones and the corresponding means of verifications.

Deliverables: Include the mandatory deliverables for this WP listed in section 10 of the Call document, in particular the annual GHG emissions avoidance report. Moreover, add any other essential deliverable suitable to report on the progress of the WP activities and the achievement of the expected GHG emissions savings.

Milestone No

(continuous numbering not linked to WP)

Milestone Name

Work Package No

Lead Beneficiary

Description

Due Date

(month number)

Means of Verification

MS1

End of second year of operation

4

Milestone triggering payment

All the previous supporting documents and deliverables for this phase, as relevant

Deliverable No

(continuous numbering linked to WP)

Deliverable Name

Work Package No

Lead Beneficiary

Type

Dissemination Level

Due Date

(month number)

Description

(including format and language)

D4.1

Annual GHG emission avoidance report

4

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

D4…

4

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

Work Package

To insert work packages, copy WP4 as many times as necessary.

Work Package N (last year of operation)

Work Package N: Last year of Operation

Duration:

MX - MX

Lead Beneficiary:

1-Short name

Objectives

Achievement of the expected GHG emissions savings.

Activities and division of work (WP description)

Task No

(continuous numbering linked to WP)

Task Name

Description

Participants

In-kind Contributions and Subcontracting

(Yes/No and which)

Name

Role

(COO, BEN, AE, AP, OTHER)

TN.1

n/a

TN.2

n/a

n/a

Milestones and deliverables (outputs/outcomes)

Milestones: Include as mandatory milestone the one triggering the payment at the end of the last year of operation. Depending on the specificities of your project, please adjust the milestones or include other relevant milestones and the corresponding means of verifications.

Deliverables: Include the mandatory deliverables for this WP listed in section 10 of the Call document, in particular the annual GHG emissions avoidance report. Moreover, add any other essential deliverable suitable to report on the progress of the WP activities and the achievement of the expected GHG emissions savings.

Milestone No

(continuous numbering not linked to WP)

Milestone Name

Work Package No

Lead Beneficiary

Description

Due Date

(month number)

Means of Verification

MS…

N

MS…

End of last year of operation

N

Milestone triggering payment

All the previous supporting documents and deliverables for this phase, as relevant

Deliverable No

(continuous numbering linked to WP)

Deliverable Name

Work Package No

Lead Beneficiary

Type

Dissemination Level

Due Date

(month number)

Description

(including format and language)

DN.1

Annual GHG emission avoidance report

N

[R — Document, report] [DEM — Demonstrator, pilot, prototype] [DEC —Websites, patent filings, videos, etc] [DATA —  data sets, microdata, etc] [DMP — Data Management Plan] [ETHICS] [SECURITY] [OTHER]

[PU — Public]

[SEN — Sensitive]

[R-UE/EU-R — EU Classified]

[C-UE/EU-C — EU Classified]

[S-UE/EU-S — EU Classified]

DN.2

Verified GHG emission avoidance report over the entire monitoring period

DN….

Estimated budget — Resources

Estimated budget — Resources

See detailed budget table/relevant cost calculator (financial information file) (annex 1 to Part B).

Timetable

Timetable

Fill in the timetable for the project (using either the template available on Portal Reference Documents or a Gantt chart which respects the minimum requirements set out in the template) and attach it to your Application Form (annex X to Part B).

See timetable/Gantt chart (annex X to Part B).

#§WRK-PLA-WP§#

#@ETH-ICS-EI@#

8. OTHER

8.1 Ethics

Ethics

Not applicable.

#§ETH-ICS-EI§# #@SEC-URI-SU@#

8.2 Security

Security

Not applicable.

#§SEC-URI-SU§# #@DEC-LAR-DL@#

9. DECLARATIONS

Do No Significant Harm (DNSH)

YES/NO

We confirm that we will ensure that the project will comply with the ‘do no significant harm’ technical screening criteria (TSC) set out in Annex II to Delegated Regulations 2021/2139 and/or 2023/2486.

We acknowledge and confirm that we will comply with these requirements throughout the project implementation and that in case of breach, we understand that the grant may be terminated and reduced or any other measure described in Chapter 5 of the Grant Agreement may be taken.

Cumulation of funding/Double funding

Information concerning other EU grants for this project

Please note that there is a strict prohibition of double funding from the EU budget (except under EU Synergies actions).

YES/NO

We confirm that to our best knowledge neither the project as a whole nor any parts of it have benefitted from any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details.

We confirm that to our best knowledge neither the project as a whole nor any parts of it are (nor will be) submitted for any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details.

Financial support to third parties (if applicable)

Not applicable.

PDA support

Proposals may be proposed for project development assistance (PDA) support from the European Investment Bank (EIB) as a result of the evaluation (see section 8 of the Call document).

In this case, your proposal (and all the project documentation which is submitted to us) would be shared with the EIB.

Do you agree that your proposal and the project documentation will be provided to the EIB for their PDA assessment?

[YES] [NO]

National funding schemes (also called ‘grants as a service’)

Proposals may be proposed for national schemes as a result of the EU evaluation.

This means that your proposal (and all the project documentation which is submitted to us) would be shared with the national authorities of the country where the project takes place.

Do you wish to be proposed for a national funding scheme?

Please note that, in case you agree, this will also be considered as explicit consent to the sharing of your proposal (including Part B and all annexes and the evaluation summary report) with the competent national granting authority.

[YES] [NO]

Information to Member States

Following call closure, information on the project participants, their projects, their contact details, the amount of requested Innovation Fund support and, where relevant, envisaged dates of financial close and entry into operation may be shared with the Member States of the country(ies) where the project is located, in order to facilitate Member States’ coordination of the support for projects.

Do you agree on behalf of the project consortium that this information is shared with the Member States?

[YES] [NO]

#§DEC-LAR-DL§#

ANNEXES

LIST OF ANNEXES

Standard

Detailed budget table/Relevant cost calculator (Financial information file) (annex 1 to Part B) —mandatory

Special

Timetable/Gantt chart (annex X to Part B) — mandatory

Other annexes (annex X to Part B) — mandatory, if required in the Call document

HISTORY OF CHANGES

VERSION

PUBLICATION  DATE

CHANGE

1.0

15.03.2022

Initial version (new MFF).

2.0

01.11.2022

Tags added. Update for 2022 LSC call.

3.0

01.10.2023

Update for 2023 calls.

4.0

15.11.2024

Update for 2024 calls.

5.0

01.12.2025

Update for 2025 calls.